Consultancy services for the evaluation of the Centre Regional Programme – Phase I

The Contracting Authority:

Centre Regional Development Agency

Annexes to the Report Evaluation Theme 3

Evaluation of the PR Center's interventions in the field of energy efficiency

and reducing greenhouse gas emissions

October 2025

TABLE OF CONTENTS

1.	Evaluation methods used	3

2.	Literature review	5

3.	List of documents studied	7

4.	Summary of interviews conducted	8

1.	Managing Authority PR Center	8

2.	Municipality – county seat	9

3.	City	10

4.	Specialized body	11

5.	Municipality – county seat	12

6.	County Council	13

7.	Commune	14

8.	CYNOLOGICAL Center – educational institution	15

9.	Focus Group for Funding Applicants	16

10.	Consultation of institutional stakeholders	17

11.	MA RP for the Central Region Interview (Financial Instruments Scheme)	19

12.	Panel of experts	20

5.	Portfolio of RSO2.1 contracted projects	22

6.	Cost-Benefit and Cost-EfficiencyAnalysis	26

7.	Results of the survey applied to the applicants for funding	44

8.	Case studies	45

Case study no. 1: Thermal rehabilitation of pavilion C17 – physiotherapy, child psychiatry, SMIS code 301784	47

Case study no. 2: Thermal rehabilitation Teiuș Theoretical High School - Grades I-VIII, SMIS code 325436	61

Case study no. 3: Thermal rehabilitation of apartment blocks in order to increase energy performance, 9 blocks of flats in Miercurea Ciuc, Harghita county, SMIS code 325468	73

9.	Comments on the EVALUATION Report	84

Evaluation methods used

| Documentary research | PR Center program document and implementation documents (applicant guides, project portfolio databases, call calendar, PR Center monitoring reports, minutes of Monitoring Committee meetings, etc.) Strategic documents at regional, national, European, international level: Centre Region Development Plan 2021-2027, PNIESC, SNRTL, EU Directive 2024/1275, Net Zero by 2050, etc. Specialized literature. The complete list of documents analyzed can be found in Annex 3. |
| --- | --- |
| Desk analysis | Cost-benefit analysis Cost-efficiency analysis. Both analyses are presented in Annex 6. |
| Individual interviews with applicants and members of the Monitoring Committee | 7 funding applicants, of which 2 CM members and 1 CM observer. 1 CM member. The complete list of interviews conducted, and their content can be found in Annex 4. |
| MA RP for the Central Region Interview | The information collected can be found in Annex 4. |
| MA RP for the Central Region Workshop | The information collected can be found in Annex 4. |
| Survey applied to applicants for funding | The survey was applied to a population of 23 applicants, managing a number of 54 projects at various stages (contracted, under contract, admitted to ETFs). According to the Taro Yamane formula, for a total population of 54 respondents and a planned margin of error of ±3%, approximately 51–52 responses would have been required. A number of 53 project-level responses were registered from 22 funding applicants. The poll's margin of error is about ±2%, at a 95% confidence level. The results of the survey can be found in Annex 7, attached to this document. |
| Focus group of funding beneficiaries | It brought together a number of 9 participants, representing 3 municipalities, 2 communes and a public institution. The information collected can be found in Annex 4. |
| Consultation of institutional stakeholders | It brought together four representatives of organizations and institutions involved in the promotion and implementation of energy efficiency at national level. The information collected can be found in Annex 4. |
| Case studies | 3 case studies were carried out at the level of beneficiaries. The case studies are presented in Annex 8. |
| Panel of experts | It brought together four experts in the field of energy efficiency of buildings, from the private sector. |

List of factors influencing the intervention, predefined and tested in the evaluation

INTERNAL FACTORS OF THE INTERVENTION Internal factors are elements under the direct or indirect control of the factors involved in the project (beneficiaries, MA, consultants, etc.). Design of the intervention - How to define the objectives of the intervention (clarity, coherence) - Consistency of programme indicators with the objectives of the intervention - How to transpose the objectives, priorities, conditions and indicators of the intervention into the Applicant's Guides - How to transpose the objectives, priorities, conditions and indicators of the intervention into the Technical and Financial Evaluation Grids Management of the basic processes of the intervention - Calls for projects, evaluation and selection, contracting, project monitoring, payments - Support provided to beneficiaries by MAs in the preparation and implementation stages of projects Interest in potential beneficiaries - Number of projects submitted - Quality of submitted projects - Amount of funding requested through submitted projects Capacity of beneficiaries of funded projects - Ability to design technical solutions - Quality of technical-economic documentation (energy audit, design) - Financial capacity to support the cash flow required for the implementation of the project - Project management capability according to PR Center requirements FACTORS EXTERNAL TO THE INTERVENTION External factors are conditions or influences outside the sphere of control of the intervention, which cannot be directly controlled by the factors involved in the intervention. - Relevant changes to the legal framework - Other programmes funding similar interventions - Administrative procedures for authorization (urban planning, ISU, environment, etc.) - Socio-economic factors: price evolution (materials, equipment, labor) - Capacity of suppliers of goods and services

Source: Authors

Literature review

Technological advances in the energy efficiency of buildings (2020–2025)

The literature, together with the European and national strategic sources analyzed in this evaluation, highlights significant progress in the last five years in the field of technologies applied to increase the energy efficiency and performance of buildings. These advances focus on four major directions: optimizing the building envelope, digitizing energy management systems, integrating renewables, and developing passive and intelligent solutions to adapt to environmental conditions.

The building envelope continues to be one of the key areas of innovation. Phase change materials (PCMs) are used because of their ability to regulate the interior temperature by absorbing and releasing heat. In parallel, research has led to the development of innovative composite materials, including combinations of metal-organic structures (MOFs), which offer a high thermal storage capacity and increased strength over time. These solutions are already experimentally tested in several living lab projects, confirming their role in reducing the need for artificial air conditioning.

In terms of real-world use, phase-change materials (PCMs) and MOF composites occur in two different stages:

- PCM (phase change materials) – these are already used in real projects (not just living labs), but generally on a smaller scale or experimentally in public buildings, demonstration buildings and in certain commercial office/residential projects. They are recognized as applicable technology, but they do not yet have a wide diffusion, due to the cost and complexity of installation. They are therefore also tested in the real environment but not yet generalized.

- MOF (metal-organic frameworks) – here we are mainly talking about the research stage and living labs. They are promising for thermal storage and filtration, but they are not currently used in ordinary buildings. The literature mentions them as an emerging direction, not as a solution already adopted in the energy efficiency sector.

Active technologies have seen rapid advances, especially in the field of high-efficiency heat pumps and HVAC systems integrated with artificial intelligence algorithms. The new generations of equipment allow the adjustment of the operation in real time, based on the data collected from the building (occupancy, temperature, humidity), increasing efficiency and reducing energy losses. In some EU Member States, these technologies are already being used on a pilot scale in public and residential buildings, with visible results in terms of reducing final consumption and greenhouse gas emissions.

Digitalization and Building Energy Management Systems (BEMS) are at the heart of the transition to smart buildings. The National Renovation Strategy and PNIESC 2024 promote BEMS as key solutions, especially for non-residential buildings. These systems facilitate detailed monitoring of consumption, identification of losses and automatic adjustment of equipment, ensuring proactive control and increasing the sustainability of energy savings. Moreover, recent European Directives (e.g. EU Directive 2024/1275) introduce the concept of "smart readiness" for buildings, which will stimulate the adoption of integrated energy monitoring and control platforms.

Passive and adaptive solutions complete the technological picture. In the public and residential sectors, the use of passive cooling technologies (e.g. high-emissivity coatings for radiative cooling) and adaptive tires, capable of modifying their thermal properties according to external conditions, is expanding. They significantly reduce the need for energy for air conditioning and align with the occupants' interior comfort and health goals.

Overall, recent literature shows that technological progress is not limited to equipment or materials but extends to their integration into a coherent building ecosystem, in which renewable energy solutions (photovoltaic panels, solar thermal panels, heat pumps), innovative materials and intelligent control systems work synergistically. This model supports the transition to nearly zero-energy buildings (NZEBs) and, in the longer term, to zero-carbon-ready buildings.

The European strategic frameworks (European Green Deal, Renovation Wave, EU Directive 2024/1275) and national ones (PNIESC 2024, National Renovation Strategy) strengthen these directions, setting higher standards and accelerating the shift to advanced solutions, with a focus on prosumers, smart metering and energy flexibility. Thus, Romania aligns with a broader European trend, in which the energy efficiency of buildings is not only a technical priority, but also a social and environmental one, closely linked to the objectives of decarbonization and energy resilience.

Bibliography

- European Commission. Renovation Wave for Europe – greening our buildings, creating jobs, improving lives. Bruxelles, 2020.

- European Commission. Directive (EU) 2018/844 of the European Parliament and of the Council on the energy performance of buildings (EPBD), and revised version 2024/1275.

- Ministry of Energy. National Integrated Energy and Climate Change Plan 2021–2030 (PNIESC), updated edition 2024.

- Ministry of Development, Public Works and Administration. National Strategy for Long-Term Renovation of the Residential and Non-Residential Real Estate Fund (SNRTL), 2020.

- European Investment Bank – JASPERS. Simplified Cost-Benefit Analysis for Energy Efficiency in Buildings. Technical Guide, 2023.

- European Stock Building Observatory. Statistics and reports on the energy performance of buildings in the Member States of the European Union. Available online: https://buildingstock-observatory.ec.europa.eu

- Buildings Performance Institute Europe. Future-proof buildings for all Europeans – Insights and policy recommendations, Bruxelles, 2022.

- International Energy Agency. Energy Efficiency 2022: Market Report Series, Paris, 2022.

- Academic and research reports, published in 2019–2025.

List of documents studied

- PR Center Management Authority. Centre Region Programme 2021-2027, August 2025 version.

- European Commission. Directive (EU) 2018/844 of the European Parliament and of the Council on the energy performance of buildings (EPBD), and revised version 2024/1275.

- Ministry of Energy. National Integrated Energy and Climate Change Plan 2021–2030 (PNIESC), updated edition 2024.

- Ministry of Development, Public Works and Administration. National Strategy for Long-Term Renovation of the Residential and Non-Residential Real Estate Fund (SNRTL), 2020.

- International Energy Agency. Net Zero by 2050, Paris, 2021.

- Regional Development Agency Centre. The Development Plan of the Centre Region for the period 2021-2027, 2021.

- PR Center Management Authority. Indicative calendar for the launch of calls for projects for 2025, PR Center 2021-2027, 2024

- PR Center Management Authority. RSO2.1 project portfolio databases, as of 30.04.2025

- PR Center Management Authority. Minutes of the meetings of the PR Center Monitoring Committee, 2022-2024.

- PR Center Management Authority. Mid-term analysis report of the Centre Region Programme, 2025.

- PR Center Management Authority. Report on the implementation of the Centre Region Programme, 2023, 2025.

- PR Center Management Authority. Applicant Guides, Action 3.1, Action 3.2, 2023-2024.

Summary of interviews conducted

- Managing Authority for the Centre Region Programme

1. Stage of implementation and interest of the beneficiaries

- Action 3.2 is at a more advanced stage compared to Action 3.1, which is still in the technical and financial evaluation stage.

- There was a major interest of the beneficiaries, materialized by a significant number of projects submitted, including phased projects.

- A 70% over-contracting was applied for Action 3.2, reflecting both the increased interest and the efforts of the MA to respond as best as possible to the existing demand.

2. Influencing factors and support from AM

- Success factors include clarity of objectives and implementation mechanisms, including the existence of coherent guidelines and grids.

- The problems encountered with the implementation are the usual ones (e.g. delays caused by tenders), but they are manageable and do not constitute structural barriers.

- The MA has made measures to increase administrative capacity mandatory, so that beneficiaries can better understand and manage other types of financing (e.g. financial instruments).

- The idea of creating a building user guide for the residential component was proposed, which would support the maintenance of energy performance after the completion of the works.

3. Adapting to technological advances and good practices

- No major technological advances have been reported since the launch of the PR Center; however, projects may undergo changes in the PT phase if better solutions appear.

- The inclusion of consumption monitoring systems is scored in the ETF grid, which stimulates the integration of smart technologies.

- The AM Centre has been active in exchanging European best practices, in particular through cooperation projects (e.g. Horizon, Interreg Europe, cooperation with Brandenburg, experiences on biomass in Finland).

- There was also informal interregional cooperation, through exchanges of procedures and examples with the Regional Development Agency of the Republic of Moldova.

4. Relevance and appropriateness of the intervention

- The objectives of the intervention remain perfectly aligned with the current needs, the socio-economic context not registering significant changes since the elaboration of the PR Center.

- However, the needs are greater than the available financing capacity, which justifies maintaining and even extending the intervention.

- All submitted projects aim at in-depth renovation, although the program's targets were set more conservatively (50%).

- The values of the result indicators are already almost reached or exceeded by the contracted projects, which confirms the relevance and success of the intervention.

5. Prioritization of buildings and compliance with technical conditions

- The MA applied indirect prioritization criteria, such as the year of construction (pre-2000) and occupancy, in the absence of explicit criteria related to energy performance.

- The limit of 15% for auxiliary measures was respected, by automatically excluding expenses exceeding the ceiling from the calculation of eligibility.

6. Efficiency and fairness in selection

- The MA confirmed that the total score of the project determines funding, even though some buildings in individually rejected projects would have higher scores than those in accepted projects – an inherent limitation of the competitive mechanism.

7. Horizontal principles

- The principles of sustainable development are inherently respected, due to the nature of the intervention.

- In addition, the beneficiaries included in the projects measures that exceed the minimum legal requirements, being also scored for this in the ETF grids.

- Compliance with these principles is monitored in implementation, and so far, no relevant issues have been identified.

- Municipality – county seat

1. Relevance of the intervention and local needs

- The representatives of the city hall stressed that the need for energy efficiency is high, especially in the case of old public buildings and residential buildings in areas with social vulnerability. In addition, a significant number of buildings are occupied by families with social problems, which accentuates the social dimension of the intervention.

- The objectives and conditions of the funding line are considered relevant and correctly formulated, but the level of financial allocations is insufficient to cover the real need, which is much higher.

2. Building selection and prioritization process

- The choice of buildings was made based on combined criteria, including: the age of the building, the technical expertise, the requests of the tenants' associations and the potential for maximum score in the grid (e.g. buildings in marginalized areas).

- The City Hall has a prioritization strategy in the works but recognizes the difficulty of coherently integrating all existing strategies (local, national, European).

3. Previous experience and difficulties related to co-financing

- The authority had previous experience with different sources of funding: ROP (with 40% co-financing), PNRR (100%) and PR Center (98%), which generated difficulties in the relationship with the owners' associations, due to the perception of unequal treatment.

- In some cases, the beneficiaries started the works on their own (e.g. through sponsorship), which led to the withdrawal of a project already submitted, for reasons of ineligibility.

4. Adapting to innovation and best practices

- The City Hall has integrated examples of modern technical solutions (e.g. heat pumps, photovoltaic systems) inspired by other national projects.

- There is a model of good practice on energy communities, which involves public-private partnerships and the sharing of efficient solutions (e.g. joint boilers or heat pumps). Although it has not yet been implemented, there is an intention to apply it in the future.

- Partnerships are actively sought in transnational projects through Horizon, Interreg, Urban, etc.

5. Technical design and challenges with designers

- The technical design aimed to be competitive, including elements of the New European Bauhaus principles, at the express request of the authority.

- However, it was noted that the level of designers is average, and they do not always comply with the minimum technical regulations, much less the high-quality requirements imposed by the beneficiary. There was a need for strict control by the city hall on the design mode.

6. Preparation of funding applications and administrative issues

- There were no difficulties in developing the cost-benefit analysis.

- Problems with the interpretation of some provisions of the Guide were reported, in particular:

  - the criterion of avoiding double financing, where in other RDAs5 the local budget was exempted;

  - the fixed amount of indirect expenses of 5%, which should have been formulated as a flexible maximum ceiling.

- These issues have been reported to the MA, and it is recommended to discuss them in the Monitoring Committee.

7. Role in the Monitoring Committee (CM) and strategic observations

- The representative of the city hall participates in the CM and mentioned that there were no relevant strategic discussions on cost-efficiency or substantial changes to the guidelines.

- It was stressed that the financing needs exceed the available resources and the intervention is still necessary and justified.

8. Positive factors in implementation

- The relationship with MA RP for the Central Region is considered very good, both in terms of communication and pre-financing mechanisms, clarifications and support in procurement.

- AM is perceived as prompt, engaged and professional in interactions with beneficiaries.

- City

1. Relevance of the intervention and local needs

- The analyzed project is part of a phased intervention, aiming at the complete renovation of the Theoretical High School in the locality. The first stage, financed by ROP 2014–2020, covered grades IX–XII, and the current stage (through PR for the Central Regional) targets grades I–VIII, in two distinct buildings.

- The need for renovation was determined by the degraded physical condition of the building – electrical and thermal installations over 80 years old, worn roofs and non-existent insulation. The project provides extensive work: changing the roof, thermal insulation, carpentry, lighting systems and heat pumps.

- In the case of residential blocks, the selection of buildings was made according to the existence of legally constituted owners' associations, given that most of the blocks are in a similar technical situation. The 2% co-financing is fully provided by the City Hall.

2. Defining and adapting technical solutions

- The technical solutions were developed by the designer, following the energy audit, and include highly efficient measures, such as heat pumps and photovoltaic panels. These solutions were successfully tested in the project with grades IX-XII financed by the ROP, where there was a 50% reduction in energy consumption.

- The beneficiary also took over good practice models observed in partner localities in Belgium and the Netherlands, in particular on the use of heat pumps in the rehabilitation of kindergartens or other public buildings.

3. Implementation capacity and financial effort

- The phased project started in 2019 and is scheduled to be completed in 2025. The transition from ROP to PR Center was accompanied by administrative and adaptation difficulties.

- The price increases in the post-pandemic period generated significant financial pressures, but the city hall managed to ensure co-financing and coverage of ineligible expenses through bank loans and local budget. Credit is used both as a bridge mechanism for cash flow and to absorb price differences.

- Future maintenance is not perceived as a problem, as maintenance costs already existed before the renovation and will continue to be borne in the same way.

4. Technical design and cost-benefit analysis

- The technical design was developed by the same operator who carried out the execution, based on the audit documentation. No major technical difficulties were reported.

- The cost-benefit analysis was outsourced to a consulting firm other than the designer. The trial went smoothly.

- No major changes in solutions or the need for technological upgrades were reported compared to the time of submitting the project.

5. Relationship with RDA and the administrative process

- The applicants’ guidelines were considered clear and easy to follow, and the evaluation, selection and contracting process was carried out within a reasonable timeframe.

- The beneficiary has collaborated with consulting firms for the drafting and submission of financing applications and has other energy efficiency projects underway through PNRR or LAG.

6. Implementation and lessons learned

- The implementation of the project is ongoing, and the beneficiary mentioned that he would do the same if he started the project all over again, considering the current experience as a positive one.

- The only problematic aspect remains the risk of price increases and uncertainties about future costs, but these are managed through rigorous financial planning.

- The principles of sustainable development and equal opportunities have been respected since the design phase. No difficulties were reported in this regard.

7. Information and awareness

- Constant public information activities were carried out, including press articles and the production of videos.

- The City Hall was included in a pilot project on MIBE heat pumps, which contributed to the visibility and replicability of the intervention.

- Specialized body

The entity, as a member of the Monitoring Committee of the PR Center, has been actively involved since the development phase of the Program. The interlocutors stressed that, although the current structure of the intervention is functional, it would have been appropriate for it to include a more integrated planning of actions, correlated with other relevant strategic documents (e.g. General Urban Plans), especially in the context in which energy efficiency is an essential component of territorial development.

The organization's representatives pointed out the need to capitalize locally on locally produced renewable energy, especially in the context of projects that include photovoltaic panels. According to them, it is essential that beneficiaries have a flexible set of tools that allow their own consumption of the energy produced, with the possibility of storage and intelligent management. However, the current legal framework does not sufficiently incentivize prosumers, and the necessary changes in legislation (e.g. the Prosumer Law) are still being approved.

Among the proposals made within the Monitoring Committee were:

- introduction and use of energy performance indicators;

- focus on preparing beneficiaries for future renovation projects (in the context where, in the past, the available funds have not been fully used);

- supporting measures to combat energy poverty;

- promoting real-time monitoring systems for energy consumption, in order to optimize the use of modern facilities and increase efficiency.

They also reported difficulties in obtaining data on real energy consumption, due to restrictions imposed by utility providers on GDPR grounds. This also affects the ability to correctly measure the results of projects, as the reported values of energy savings and CO₂ emission reductions are estimated based on consumption standards, not actual consumption.

At the same time, the importance of educating building users about the efficient use of energy was highlighted. Currently, the lack of tariff differentiations by time intervals reduces the motivation for smart consumption behaviors.

Regarding the quality of the technologies used, the interviewees appreciate that the funded projects contain solid solutions, but many of them are not practically tested before implementation. The example was given of private developers who build blocks without gas connection, relying exclusively on photovoltaic panels and heat pumps with floor distribution – a solution with only 10% higher costs, but with significant operating benefits.

Finally, they pointed out that there is no adequate monetization of the social benefits of renovation, which limits the real evaluation of investment efficiency and artificially extends the estimated payback period.

- Municipality – county seat

The City Hall is a beneficiary with solid experience in the field of energy efficiency, implementing an extensive portfolio of projects financed through various sources – PR Center, PNRR, Swiss and Norwegian funds. The current interventions include both rehabilitation of historic buildings (e.g. the "Maria Tereza" building) and educational units (e.g. I.L. Caragiale School, Kindergarten 15), and some of these involve consolidation and functional reconfiguration works.

The selection of buildings was based on a strategic approach, based on the energy plan developed at the level of the UAT. Through this plan, public buildings were prioritized according to energy efficiency and functional importance, and the city hall is up to date with the implementation of the action plan assumed until 2030. The buildings that have not yet been included in renovation projects are those over which the UAT does not have ownership.

As for the technical solutions, the beneficiary applied the lessons learned from 2014–2020 and took over previously validated solutions (air-to-water heat pumps, heat recovery units, basement and attic insulation). These are now considered "classics" and are complemented with more advanced equipment available on the market. Energy auditors have a decisive role in choosing solutions, and designers generally comply with the requirements formulated by the procurement documentation. The exceptions are related to compliance with ISU requirements, which may influence design details (e.g. choice of joinery with aluminum profiles).

The process of developing technical projects is advanced – in most cases, the TP was already completed at the time of contracting, allowing for the rapid initiation of procurement. However, there were significant difficulties in procurement procedures – including appeals and cancellations – which led to lengthy extensions (more than 6 months).

The beneficiary manages the works flexibly, adapting their development according to the realities on the ground – including working on floors or temporarily moving children to other spaces or containers. Measures have been taken such as the outsourcing of meal services (catering) for kindergartens during the construction period.

The application of horizontal principles is considered routine: all projects include measures for people with disabilities, but also educational and visual elements to promote environmental protection, especially in schools. These measures go beyond the minimum requirements and reflect a proactive and creative approach.

The process of developing the Cost-Benefit Analysis (CBA) did not generate difficulties, being outsourced and correlated with the development of the technical project or DALI. The estimates in the application for funding (CF) on the duration of implementation have proven to be realistic – in general, projects are planned for a duration of 12 months.

- County Council

It is an experienced beneficiary, in the midst of implementing several energy rehabilitation projects for medical units, including the County Hospital, with an extensive and complementary portfolio of interventions between PR Center and PNRR. The projects are carried out in parallel with the current activity of the hospital units, which implies rigorous planning and operational adaptability.

The selection of the buildings was made based on their functionality and the urgency of the necessary works, and the technical solutions were chosen through a combination of internal expertise (own engineers) and proposals from the designers. The Council has specialized internal resources (construction engineer, installation engineer), which facilitates the validation and adjustment of the proposed solutions in the projects.

Among the lessons learned from the ROP 2014–2020 period are the difficulties generated by the works carried out in functional buildings, which has led the county authority to now approach the works in a phased manner, with the isolation of some sectors of the floors, in an effort to minimize the impact on patients and staff. However, these measures slow down the pace of implementation, which was not always correctly estimated in the initial planning phase.

The interlocutors stressed that limitations on the eligibility of expenditure for ancillary measures (e.g. the 15% ceiling) constitute a significant constraint, especially in the case of hospital buildings that require complex work and comply with additional regulations. Attempts to combine several sources of funding have proven ineffective in practice. Also, one project was withdrawn due to very high co-financing costs, and another was redirected from the PNRR to PR Centre due to restrictions on costs per square meter.

In order to cover the ineligible costs and co-financing, the CJ representatives resorted to alternative sources, including bank loans and sponsorships (e.g. TransGaz). The implementation is going "ok", being helped by the experience gained and by a well-established internal team.

Although it was not possible to fully take over the technical models from the external visits (e.g. hospitals in Germany and Poland), some solutions seen there were still introduced, such as photovoltaic panels (PV) for the Transylvania Hall or shading systems applied at the County Hospital. The Council expressed its intention to learn more from European examples in the future by participating in fairs and other forms of technical cooperation.

The criticisms made by the CJ representatives within the Monitoring Committee (CM) refer to the fact that, from one programming period to another, a real simplification of the procedures was not achieved. The beneficiary considers that the current approach, imposed by the Commission, does not place sufficient emphasis on flexibility of results, but focuses on rigid conditionalities and uniform standards.

- Commune

The administrative-territorial unit submitted three in-depth energy rehabilitation projects for educational units, in the context of an extensive portfolio of public investments (PNRR, Anghel Saligny, POIM, POCU, AFIR). The buildings concerned are old, with an advanced degree of physical and moral wear, outdated technical systems and a low level of energy efficiency (classes C, E and F), requiring integrated interventions to achieve energy class B and reduce energy consumption and CO₂ emissions by more than 60%.

The beneficiary selected the buildings in the educational field based on the local priority given to education and environmental quality in schools, in the absence of an external project model – the projects were built starting from the individual analysis of each building and adapted to the local specificity. The measures envisaged include complete envelopes, ground-to-water heat pumps, photovoltaic panels, integrated building automation system (BMS), interior repartitioning and compliance with ISU requirements and accessibility.

The City Hall emphasizes that the objectives of PR Center correspond only partially to the real needs of the beneficiary. The major constraints are related to the capping at 15% of the eligible expenses for auxiliary works (e.g. consolidation, network restoration, waterproofing), although these works are essential for the functionality and durability of the intervention. For the historic buildings in the commune, this ceiling generates a disproportionate financial effort, including the need to take out loans.

The process of preparing the financing application was considered complex and bureaucratic, with no significant improvements compared to the 2014–2020 period. The beneficiary also notes the excessive rigidity of the evaluation and contracting stages, with requests for clarifications considered unduly detailed (e.g. models redone for insignificant variations). The same rigidity manifests itself in relation to any intention of technological adaptation – even minor changes to DALI are rejected or considered ineligible, discouraging useful upgrades.

The projects are at an early stage. For one of the schools, the order to start the work was issued, and the other two are in the acquisition stage. The implementation is managed by a mixed team (internal + consultants), with a focus on supervising procurement procedures and adapting the calendar according to the temporary relocation of students.

The beneficiary identifies several positive factors: previous experience in projects, management involvement, effective collaboration between the team and the school, solid technical documentation. On the other hand, important risk factors are reported: high costs for own contribution, risks related to execution companies, delays due to acquisitions and lack of adequate space for the temporary relocation of students.

The projects integrate horizontal principles: adaptation for people with disabilities (tactile, visual, motor), local partnerships for the prevention of bullying, and inclusive educational activities for children from diverse backgrounds. Information activities will take place at a later stage.

In conclusion, the commune proves a high level of commitment, but also a structural vulnerability to the additional financial effort. The lessons learned underline the importance of sound technical documentation, realistic planning and a more effective dialogue between beneficiaries and the managing authority.

- Cynological Centre – educational institution

The Center implements its first energy rehabilitation project, targeting a school pavilion with mixed functions (accommodation and training). The building is about 75 years old and has not benefited from major rehabilitation works for almost two decades. Currently, due to its physical condition, space is only partially used, its duties being partly taken over by another building on the premises. Through this project, the institution aims to bring the pavilion to modern standards and restore its full functionality.

Although the institution has no previous direct experience with projects of this type, the coordinator mentioned the experience gained in similar projects from the previous period, (ROP 2014–2020 and PNRR). In addition, the Center has also accessed other sources of financing for the energy transition – in particular through the Modernization Fund (for the installation of a photovoltaic park) – and intends to apply for new funds (e.g. Swiss funds), which denotes a constant institutional interest in investments in energy efficiency.

The planned works include interventions on the roof, basement, carpentry, consolidation works, installation of fan coils and heat recovery units, as well as the adaptation of the building for the access of people with disabilities. Although the technologies are not innovative, they are appropriate to the intended functionality and contribute to the objectives of energy efficiency and comfort.

The center carries out the project preparation activities in an exemplary manner with its own resources: the procurement for DALI, energy audit, technical expertise, as well as the financing application, were developed internally. Currently, the procedures for awarding advertising, financial audit, project management services are underway, and the award of the design and execution contract (16 months) is to be awarded.

The team does not anticipate major risks, relying on the support of the future consulting firm for project management. However, given that this is the first project of its kind at the level of the institution, and the works are complex, it is expected that during the implementation challenges related to coordination, procurement or execution will arise.

The project is justified by the real need to rehabilitate the educational infrastructure and contributes to the expansion of the functional capacity of the institution. At the same time, the involvement of its own team in all preparatory stages indicates a high level of ownership and an efficient approach from the perspective of administrative capacity. This experience can be good practice for other similar public entities that have in-house technical expertise and can manage the process without external consultants in the preliminary phases.

- Focus Group for Funding Applicants

The meeting was attended by nine representatives of the potential and current beneficiaries of the intervention – coming from three municipalities, two communes and one public institution – with experience in preparing and implementing energy efficiency projects. The moderator presented the general objectives of the intervention and the purpose of the evaluation, emphasizing the importance of participatory analysis to identify lessons learned and common challenges.

Participants unanimously appreciated the high relevance of the intervention, considering that it responds directly to the real needs of local authorities and public institutions, especially in the context of rising energy costs and carbon reduction requirements. Programmes financed through the PR Centre and other instruments (e.g. PNRR, Swiss funds) are perceived as complementary and well aligned with local energy transition objectives.

The discussions continued to focus on the criteria and methods of selecting the buildings proposed for renovation. In general, the participants showed that the prioritization was made based on energy consumption – with priority being given to buildings with high energy losses or major structural deficiencies – but also according to the technical condition and social role of the building (schools, kindergartens, administrative buildings). In the case of apartment blocks, the criteria were also influenced by administrative factors: the agreement of the owners, the availability of tenants' associations and the order of submission of financing applications.

In terms of technical solutions, all participants confirmed the decisive role of energy designers and auditors in configuring the appropriate technological mix for each type of building. For historic buildings, customized solutions were needed, compatible with the architectural specificity, as the application of modern technologies (e.g. heat pumps, high-performance carpentry, reclaimed ventilation systems) must at the same time comply with the requirements of heritage conservation. The experience gained in previous projects, financed by ROP 2014–2020 or by PNRR, has significantly contributed to improving the selection of solutions and avoiding the errors encountered in the first generation of projects.

The temporary relocation of building users during the works was considered a challenge successfully managed through pragmatic solutions – for example, moving children from one kindergarten to another or temporarily organizing the activity in other locally available spaces.

The most common challenges mentioned by the participants are of a financial and operational nature. On the financial side, the difficulties stem from the need to cover ineligible costs and own contributions, especially given that most local authorities simultaneously implement several projects with significant budgetary requirements. On the operational side, the main problem is the unpredictable duration of public procurement procedures, with the risk of appeals and delays affecting the execution schedule.

Other difficulties mentioned concerned the identification of qualified contractors for complex works, in particular on heritage buildings, as well as delays caused by obtaining building permits, ISU approvals or environmental agreements. Some participants mentioned the prudent practices of prior validation of procurement documentation with ANAP, as a preventive measure to reduce the risk of procedural errors.

Factors that contribute positively to the successful implementation of projects include the high experience of the implementation teams, the constructive collaboration with the issuing authorities of permits and permits, as well as the rigorous planning of activities. At the same time, for the projects for the rehabilitation of apartment blocks, some municipalities have signaled difficulties in communication and mobilization of owners' associations, especially in the stages of preparing documentation.

In a few cases, situations have been reported in which the general contractor has encountered financial difficulties, which has led to delays in the execution of the works. On the other hand, where the projects are already completed, the beneficiaries have confirmed that they have achieved real savings on energy bills, which confirms the technical and economic efficiency of the interventions.

- Consultation of institutional stakeholders

The meeting was attended by four representatives of the main organizations and institutions involved in the promotion of energy efficiency at national level: the Ministry of Development, Public Works and Administration (MDLPA), the Association of Energy Cities in Romania (OER), the Association of Cities in Romania (AOR) and the Association for the Promotion of Energy Efficiency in Buildings (ROENEF). The consultation aimed to collect opinions and recommendations on the strategic relevance, alignment directions and implementation challenges of the PR Center intervention related to the specific objective of RSO 2.1 – "Promoting energy efficiency measures in buildings".

The moderator opened the discussion with a brief presentation of the design and current status of the intervention, emphasizing that Priority 3 of the PR Center has a total allocation of approximately 120 million euros, of which about 100 million through the grant scheme and 21 million through financial instruments. The intervention covers two major categories of investments – public buildings and residential buildings – and by the time of the consultation, about 60 projects had already been contracted or were in the process of being contracted, distributed relatively evenly between the two types of beneficiaries.

Participants analyzed recent developments in the field of European and national energy efficiency policies, stressing the need for regional interventions to be linked to the new strategic documents. Currently, the new National Building Renovation Plan is being developed, the final version of which is expected for the end of 2026, as well as an updated version of the PNIESC (National Integrated Energy-Climate Plan), published in October 2024. At the same time, Directive (EU) 2024/1275 on the energy performance of buildings introduces ambitious targets for decarbonization and renovation of the built stock, but this has not yet been transposed into national legislation.

From the perspective of implementation, the institutional representatives underlined the importance of having a coherent system for monitoring and reporting progress on energy efficiency at the level of the entire country. Currently, data is collected in a fragmented manner, at the level of each administrative-territorial unit, which does not allow an aggregated picture of the renovated areas, the energy savings achieved and the types of technical solutions applied. The need for a unified national database, fed by all relevant programmes (PR, NRRP, Norwegian funds etc.), was highlighted, allowing the tracking of key indicators and the comparability of results.

At the same time, the participants noted that the built fund includes numerous buildings in an advanced state of degradation, some even abandoned, for which simple energy rehabilitation is not a sufficient solution. In their opinion, it would be appropriate for regional programmes – including the PR Centre – to allow for integrated approaches, combining energy efficiency with major renovation works, functional conversion or, where appropriate, even demolition and reconstruction. At the same time, in order to achieve the minimum energy savings target (at least 30%), it is essential to use high-performance technological solutions, validated by solid energy studies.

Another aspect highlighted was the need to monitor real energy consumption before and after the renovation, in order to objectively assess the efficiency of the interventions and the quality of the execution of the financed works. Participants recommended that the post-implementation monitoring process should become a mandatory component of future programmes, not just a voluntary activity.

Attention was also drawn to the fact that certain public buildings no longer functionally correspond to the current norms, and, in such cases, the exclusive financing of energy rehabilitation should be avoided, being more efficient to reconsider the destination of the building or its structural reconfiguration.

Regarding the factors influencing the efficiency of project implementation, the participants mentioned first of all the significant increase in construction costs and materials. The cost standards used in the PNRR, based on the ROP 2014–2020 values, no longer reflect the post-pandemic economic reality, and this gap creates pressures on the beneficiaries' budgets and on the financial feasibility of projects. Adjusting these standards and linking them to market developments would be a prerequisite for ensuring a sustainable pace of implementation.

In conclusion, the consultation highlighted the consensus among institutional actors on the need for a more integrated, data-driven approach adapted to the current economic context, in order for regional energy efficiency interventions to generate measurable and sustainable impact.

- MA RP for the Central Region Interview (Financial Instruments Scheme)

The interview focused on the financial instruments scheme related to the RSO 2.1 intervention within PR Centre, a complementary component of the grant scheme aimed at increasing the energy efficiency of buildings. The discussion clarified the design stages, the operationalization stage and the main challenges associated with this new instrument, managed for the first time by the Centre RDA.

The scheme was initially designed to support investments made by public institutions, but later the eligibility area was extended to single-family homes, based on a feasibility study prepared by the European Investment Bank (EIB). In the medium term, there is the possibility of extending the scheme to multi-family residential buildings, apartment blocks, depending on the results obtained and the institutional capacity for implementation.

An important advantage of this component is the flexibility of eligible expenses: the financial instruments scheme allows the financing of auxiliary works in a percentage of up to 30% of the total eligible expenses, unlike the grant scheme, where the ceiling is 15%. This difference gives the beneficiaries a greater margin to cover related works necessary to complete the investments – for example, minor structural repairs, adaptations of internal networks or restoration of finishes.

At the time of the interview, specific selection or eligibility criteria for this scheme other than those applicable under the grant component had not yet been defined. The establishment of these criteria is planned subsequently, in correlation with the details of the implementation agreement to be agreed between the Centre RDA and the EIB. It was noted that the collaboration agreement with the EIB does not yet have a predetermined completion date and is still in the process of technical and legal clarification.

From an operational perspective, the implementation of the scheme represents a premiere for the Centre RDA, which has not previously managed loan-type financial instruments. Thus, a period of institutional adaptation is expected, in order to strengthen the necessary administrative and monitoring mechanisms.

According to the current parameters, the maximum amount of financing granted through the loan is 30,000 euros per single-family dwelling, an amount considered adequate to cover standard energy rehabilitation investments, but which could require subsequent adjustments depending on the evolution of prices on the construction market.

During the interview, the possible risk factors that can influence the degree of implementation of the scheme were also discussed. These included: the uncertain economic context, including rising prices for construction materials, beneficiaries' reluctance to take out a loan, as well as the limited administrative capacity of some beneficiaries to manage the financial and procedural obligations of such an instrument. At the same time, it was stressed that the success of the implementation will largely depend on the information and counseling campaigns that will accompany the launch of the scheme, in order to increase the degree of understanding and trust on the part of potential beneficiaries.

In conclusion, the financial instrument scheme represents an innovative initiative in the PR Centre portfolio, aimed at diversifying the support modalities and attracting additional resources in the field of energy efficiency. Although still at an early stage, it has the potential to become a valuable complementary tool, provided that a clear, predictable implementation framework adapted to the socio-economic realities of the region is ensured.

- Panel of experts

The meeting was attended by four experts in the field of energy efficiency of buildings, from the private sector.

The moderator opened the meeting with a brief presentation of the intervention, recalling that Priority 3 of PR Center has a total allocation of approximately 120 million euros, of which about 100 million through the grant scheme and 21 million through financial instruments, covering two major areas of intervention: public buildings and residential buildings. Until the time of the discussion, under the grant scheme there were about 60 projects contracted or in the process of being contracted, distributed evenly between the two types of buildings.

The main findings and recommendations made during the evaluation were presented, and all participants unanimously supported these conclusions, appreciating their relevance and the high degree of accuracy in reflecting the realities on the ground. The experts highlighted, in particular, the fact that the intervention of the PR Center is positively distinguished by the integrated approach of investments, which allows the financing not only of energy efficiency works, but also of auxiliary works necessary for the functionality and safety of buildings. This flexibility is considered an element of good practice that should also be maintained in future programmes.

Participants also stressed the need to accelerate progress in the field of energy efficiency for single-family homes, a segment still considered insufficiently supported at national level. The moderator mentioned, in this context, the fact that PR Centre is preparing a scheme of financial instruments dedicated to this type of housing, which will complement the existing grant scheme and will contribute to the diversification of the types of support available.

A recurring theme in the discussions was the integration of renewable electricity storage solutions, especially in the case of buildings that already have photovoltaic panels. The experts drew attention to the fact that the legislation on prosumers has not evolved favorably lately, generating difficulties in grid integration and determining the installation of "off-grid" systems that reduce the overall efficiency of investments. It was agreed that the development of smart storage mechanisms should become a priority, including in regional funding programmes.

Participants also supported the recommendation of the evaluation on the financing of demonstration projects for nearly zero-energy buildings (NZEBs). Relevant international examples were brought forward, including a building in Vienna – a rehabilitated old building that managed to reach the NZEB standard through significant investments and the use of innovative technologies, demonstrating that reaching this level is possible even for historic buildings, if the technical solutions are well calibrated.

The panel also mentioned recent strategic developments at national level, including the adoption of Romania's Hydrogen Strategy, which opens up new opportunities for the integration of alternative energy sources in public and residential buildings. In this context, experts recommended that the scheme of financial instruments under preparation should include a rebate capital component, aimed at stimulating beneficiaries by providing partial non-reimbursable support. The moderator confirmed that this component is already provided for in the design of PR Centre's financial instruments scheme, dedicated to the energy efficiency of single-family public and residential buildings.

Another aspect considered essential for the sustainability of the results is the education of consumers regarding responsible behavior and rational use of energy. Participants stressed that investments in infrastructure must be accompanied by information and training campaigns aimed at changing consumption habits, so that the benefits of energy savings materialise in the long term.

Overall, the panel reflected a strong consensus among experts on the need for an integrated approach, combining technical investments with education, innovation and legislative adaptation measures. PR Center appreciated its ability to introduce new, flexible and results-oriented tools in the field of energy efficiency of buildings.

Portfolio of RSO2.1 contracted projects

| No | SMIS Code | Project Title | Contract Signing Date | Leader | Total Eligible Budget (LEI) | Total Ineligible Budget (LEI) | Total Project Value (LEI) |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | ACTION 3.2 – ENERGY EFFICIENCY IN PUBLIC BUILDINGS |  |  |  |  |  |
|  | 308787 | Energy renovation of the Transilvania Sibiu Multipurpose Hall | 27.6.2024 | SIBIU COUNTY | 62,195,576.23 | 308,685.83 | 62,504,262.06 |
|  | 311356 | MODERNIZATION OF THE CULTURAL CENTER WITH ENERGY AND STRUCTURAL REHABILITATION IN SÂNTIMBRU COMMUNE | 8.8.2024 | SANTIMBRU COMMUNE | 7,156,412.02 | 5,552,945.26 | 12,709,357.28 |
|  | 308554 | Rehabilitation of the I.L.Caragiale Secondary School in order to improve energy efficiency | 31.7.2024 | SIBIU MUNICIPALITY | 9,982,730.09 | 3,672,961.14 | 13,655,691.23 |
|  | 305896 | Energy renovation of the Administrative Pavilion within the Sibiu County Emergency Clinical Hospital | 5.10.2024 | SIBIU COUNTY | 18,720,412.13 | 309,238.12 | 19,029,650.25 |
|  | 303572 | new THERMAL REHABILITATION OF BUILDING C16 – PSYCHIATRIC PAVILION V WITHIN THE CLINICAL PSYCHIATRIC HOSPITAL DR. GHE. PREDA SIBIU | 21.3.2024 | SIBIU COUNTY | 11,275,778.26 | 1,944,321.20 | 13,220,099.46 |
|  | 305314 | REHABILITATION OF THE KINDERGARTEN WITH EXTENDED HOURS NO. 15, IN ORDER TO IMPROVE ENERGY EFFICIENCY, STR. GLADIOLELOR NR. 13A | 31.7.2024 | SIBIU MUNICIPALITY | 11,440,652.33 | 1,012,121.89 | 12,452,774.22 |
|  | 301768 | INCREASING ENERGY EFFICIENCY AND SMART ENERGY MANAGEMENT IN BERGHIA SCHOOL, PĂNET COMMUNE | 26.7.2024 | PĂNET COMMUNE | 4,788,052.86 | 719,289.22 | 5,507,342.08 |
|  | 319338 | Rehabilitation, arrangement and functional improvement of primary and preschool school units, Richis village, Biertan commune, Sibiu County | 23.10.2024 | COMMUNE BIERTAN | 8,517,689.82 | 361,286.38 | 8,878,976.20 |
|  | 318693 | Energy efficiency, consolidation and modernization of "Petru Rares" High School, Feldioara, Building A | 30.4.2025 | COMUNA FELDIOARA | 29,030,937.35 | 10,353,431.46 | 39,384,368.81 |
|  | 308475 | REHABILITATION OF THE GYMNASIUM SCHOOL NO. 23 IN ORDER TO IMPROVE ENERGY EFFICIENCY | 31.7.2024 | SIBIU MUNICIPALITY | 6,959,878.28 | 552,117.09 | 7,511,995.37 |
|  | 302296 | Rehabilitation of the Kindergarten with extended hours no. 29 to improve energy efficiency | 14.6.2024 | SIBIU MUNICIPALITY | 10,923,297.49 | 1,320,576.36 | 12,243,873.85 |
|  | 305342 | REHABILITATION OF MARIA TEREZA BUILDING - GLADIOLELOR STREET NO. 4 AND NO. 6 SIBIU | 27.9.2024 | SIBIU MUNICIPALITY | 44,376,460.17 | 26,188,864.79 | 70,565,324.96 |
|  | 304870 | Rehabilitation of the Kindergarten with extended hours Căsuța Poveștilor in order to improve energy efficiency | 30.8.2024 | SIBIU MUNICIPALITY | 10,064,573.34 | 1,531,889.33 | 11,596,462.67 |
|  | 318368 | Rehabilitation of the School with grades I-IV Biertan | 15.10.2024 | COMMUNE BIERTAN | 11,691,921.60 | 2,315,686.81 | 14,007,608.41 |
|  | 309068 | Energy renovation of the building of the Dental Polyclinic within the Sibiu County Emergency Clinical Hospital | 30.9.2024 | SIBIU COUNTY | 9,890,446.96 | 54,398.37 | 9,944,845.33 |
|  | 318875 | Increasing the energy efficiency of the School Pavilion 42-12-02 within the "Dr. Aurel Greblea" Kennel Club in Sibiu | 30.4.2025 | THE DOG KENNEL CENTER "DR. AUREL GREBLEA" SIBIU | 13,817,688.61 | 8,746,085.12 | 22,563,773.73 |
|  | 301771 | THERMAL REHABILITATION OF BUILDING C8 – POLYCLINIC WITHIN THE CLINICAL PSYCHIATRIC HOSPITAL "DR. GHE. PREDA" SIBIU | 21.3.2024 | SIBIU COUNTY | 8,801,860.98 | 1,041,102.80 | 9,842,963.78 |
|  | 301784 | Thermal rehabilitation of pavilion C17 – physiotherapy, child psychiatry | 15.5.2024 | SIBIU COUNTY | 45,760,830.34 | 629,776.29 | 46,390,606.63 |
|  | 304788 | Rehabilitation of Biertan Secondary School | 29.4.2024 | COMMUNE BIERTAN | 16,025,906.70 | 2,367,160.28 | 18,393,066.98 |
|  | 304342 | Rehabilitation of the Kindergarten with extended hours no.36 in order to improve energy efficiency | 4.6.2024 | SIBIU MUNICIPALITY | 7,201,454.09 | 794,711.73 | 7,996,165.82 |
|  |  | CALL FOR PHASED PROJECTS - ACTION 3.1 ENERGY EFFICIENCY IN RESIDENTIAL BUILDINGS |  |  |  |  |  |
|  | 325468 | Thermal rehabilitation of apartment buildings in order to increase energy performance, 9 blocks of flats in Miercurea Ciuc, Harghita county | 3.7.2024 | MIERCUREA-CIUC MUNICIPALITY | 2,942,745.07 | 1,992,752.10 | 4,935,497.17 |
|  | 325550 | Thermal rehabilitation of some residential blocks in Gheorgheni Municipality: Florilor District, blocks 45E, 49, 43, 44, 46, 51, Bucin District, blocks 18,6,11,3 - Stage II. | 29.7.2024 | GHEORGHENI MUNICIPALITY | 15,116,875.75 | 1,998,038.91 | 17,114,914.66 |
|  | 325888 | Increasing the energy efficiency of a number of six apartment blocks in the town of Bălan, Harghita County | 9.7.2024 | BALAN CITY | 1,557,009.00 | 2,602,604.81 | 4,159,613.81 |
|  | 325551 | Thermal rehabilitation of some residential blocks in Gheorgheni Municipality: Dr. Fejér Dávid nr.7, Miron Cristea nr. 8, Miron Cristea 9-11, Lacu Rosu Boulevard no. 5B, Bucin District, blocks 10,20,23,24,12 - Stage II. | 26.7.2024 | GHEORGHENI MUNICIPALITY | 5,626,410.05 | 1,292,239.40 | 6,918,649.45 |
|  | 335559 | Increasing the energy efficiency of residential buildings in Fagaras Municipality, Brasov County | 31.10.2024 | FAGARAS MUNICIPALITY | 3,481,958.06 | 1,698,409.14 | 5,180,367.20 |
|  |  | CALL FOR PHASED PROJECTS - ACTION 3.2 ENERGY EFFICIENCY IN PUBLIC BUILDINGS |  |  |  |  |  |
|  | 324767 | Increasing the architectural-environmental quality and thermal rehabilitation - "Mihai Viteazul" National College - Boarding School and Festivities Hall | 19.7.2024 | SFANTU GHEORGHE MUNICIPALITY | 1,863,179.26 | 35,700.00 | 1,898,879.26 |
|  | 325436 | THERMAL REHABILITATION TEIUȘ THEORETICAL HIGH SCHOOL - GRADES I-VIII | 11.7.2024 | TEIUŞ CITY | 2,985,878.66 | 975,700.55 | 3,961,579.21 |
|  | 325376 | Thermal rehabilitation of some buildings within the Sibiu County Emergency Clinical Hospital | 24.7.2024 | SIBIU COUNTY | 25,267,649.29 | 4,715,129.00 | 29,982,778.29 |
|  | 325470 | Rehabilitation of József Attila Secondary School | 8.7.2024 | MIERCUREA-CIUC MUNICIPALITY | 1,314,720.72 | 3,100,473.38 | 4,415,194.10 |
|  | 335523 | Rehabilitation and modernization of the hospital building Zlatna City | 31.10.2024 | ZLATNA CITY | 2,015,240.93 | 8,608,777.74 | 10,624,018.67 |

Source: PR Center Managing Authority

Cost-Benefit and Cost-Efficiency Analysis

This section includes the cost-benefit analysis (CBA) carried out within the evaluation of interventions in the field of energy efficiency of buildings financed by the Centre Regional Programme. The purpose of this analysis was to assess, on an economic and financial basis, the ratio between investment costs and benefits generated over time, both for beneficiaries and for society as a whole.

The analysis was carried out for three representative projects – the "Dr. Gheorghe Preda" Psychiatric Hospital in Sibiu, the Teiuș Theoretical High School and the complex of apartment blocks in Miercurea Ciuc – selected as case studies reflecting the typological diversity of interventions (public buildings in health, education and residential buildings). An aggregated analysis of the entire intervention was also developed to assess the overall economic efficiency of the programme and identify common patterns of cost-efficiency and climate impact.

The cost-benefit analysis was mainly carried out on the basis of a simplified methodology in line with the recommendations of the European Commission, the European Investment Bank and JASPERS, while taking into account the methodology of the European Commission (Guide to Cost-Benefit Analysis of Investment Projects, 2021) and the European Investment Bank (The Economic Appraisal of Investment Projects at the EIB, 2023). The parameters used – the 3% discount rate, the 30-year analysis period, the energy reference price of €120/MWh and the social carbon cost trajectory (€165–800/tCO₂) – are in line with these reference sources.

The results presented in this annex provide a solid basis for interpreting the conclusions in the main body of the report, illustrating in a practical way how investments contribute to the objectives of energy efficiency, reduction of greenhouse gas emissions and improvement of the quality of life in the Centre Region.

Cost-benefit analysis (CBA) – Case study 1

Project: Thermal rehabilitation of pavilion C17 of the "Dr. Ghe. Preda" Sibiu – physiotherapy, child psychiatry (SMIS code 301784)

1. Purpose and objectives of the project

The project aims to increase the energy efficiency of pavilion C17 within the "Dr. Gheorghe Preda" Psychiatric Hospital in Sibiu, through thermal rehabilitation works, modernization of the thermal installation, installation of solar thermal and photovoltaic panels, as well as other interventions that contribute to reducing energy consumption and improving thermal comfort.

The investment has the following main objectives:

- reduction of primary energy consumption by 60.15% compared to the initial situation;

- reducing annual greenhouse gas emissions by 80.52%;

- improving comfort and health conditions for patients and medical staff.

2. Input data and working assumptions

| Element | Value/Assumption |
| --- | --- |
| Total project value | RON 46,390,606.63 ≈ EUR 9.28 million (exchange rate RON 5/EUR) |
| Project implementation period | 2024-2027 |
| Duration of analysis | 30 years (2027–2056) |
| Discount rate | 3% |
| Rehabilitated usable area | 6,281.9 m² |
| Initial Annual Primary Energy Consumption | 4,068 MWh/year |
| Annual primary energy consumption after renovation | 1,622.86 MWh/year |
| Reduction compared to the initial situation | −60.15% |
| Annual energy savings | ≈ 2,445 MWh/year |
| Initial GHG emissions (tons CO₂ equivalent /year) | 634 t/year |
| GHG emissions after renovation (tons CO₂ equivalent /year) | 123.5 t/year |
| Reduction of emissions compared to the initial | −80.52% |
| GHG emissions avoided annually (tons CO₂ equivalent /year) | ≈,510.5 t/year |
| Dominant energy source | Natural gas and electricity |
| Energy price | 120 EUR/MWh (EIB/JASPERS reference value) |

3. Methodological framework applied

The analysis was carried out according to the simplified JASPERS methodology for energy efficiency projects in buildings, adapted to the specifics of the PR Center program. The main methodological elements are:

- Costs include the total amount of the investment.

- The direct benefits are represented by the annual primary energy savings, valued at a constant price of €120/MWh. An average price of €120/MWh, constant in real terms during the analysis, was used to assess the economic benefits. The value corresponds to the average reference level used in the economic analyses of the European Investment Bank (EIB) and in the JASPERS studies for energy efficiency projects, reflecting the full cost of energy (gas + electricity), without the temporary effect of capping schemes or subsidies applicable to residential consumers. This approach ensures the comparability of the results with other similar analyses at European level and a conservative estimation of the benefits, avoiding underestimating the value of energy savings in the context of the possible long-term increase in energy prices.

- The benefits of reducing CO₂ emissions are assessed by applying the European Investment Bank's (EIB) recommended benchmarks for the social cost of carbon (€165/t in 2025, progressively increasing to €800/t in 2050, thereafter kept constant).

- The indirect social benefits (thermal comfort, working conditions, health, educational environment, etc.) were estimated by applying a conservative multiplier coefficient of 1.0× to the value of the energy savings. This approach is aligned with the simplified practices recommended by JASPERS and the EC methodology for cost-benefit analysis (2014) and is frequently used in similar projects when specific data for monetization of social effects are lacking.

- The discount rate used for all feeds is 3%. The 3% discount rate is in line with the recommendations of the European Commission (Guidance for the Cost-Benefit Analysis of Investment Projects, 2014) and the European Investment Bank (EIB, 2023) and is used as standard for the evaluation of public investments in the Member States of the European Union. This rate reflects the value of time and the social preference for current consumption, representing the reference level used in economic analyses for projects with non-reimbursable financing.

- The 30-year analysis horizon corresponds to the economic lifespan of investments in the energy renovation of buildings.

4. Results of the cost-benefit analysis

4.1. Financial analysis

The financial analysis assesses the sustainability of the investment in terms of energy savings flows, without including own grants or contributions.

| Indicator | Value |
| --- | --- |
| Net present value (NPV_fin, 3%) | −€3.53 million |
| Internal Financial Rate of Return (FIRR) | ≈ −0.4% |

The results show that the project is not financially attractive in the absence of non-reimbursable financing, which is common for energy efficiency projects in public buildings, where the economic and social benefits far outweigh the purely financial benefits.

4.2. Economic analysis

Economic analysis includes, in addition to financial savings, positive social and environmental effects.

| Component | Updated value (mln. EUR) |
| --- | --- |
| Energy savings | 5,75 |
| Indirect social benefits (1.0×) | 5,75 |
| Reduction of CO₂ emissions (EIB cost of carbon) | 4,82 |
| Investment costs | −9.28 |
| Economic Net Present Value (NPV_econ) | +7.04k EUR |
| Internal Economic Rate of Return (EIRR) | ≈ 7.6% |

According to the JASPERS interpretation grid:

- ERR < 3,5% – slab

- 3.5–5% – acceptable

- 5–7% – good

- 7–10% – Very good

- >10% – excellent

The analyzed project falls into the "Very Good" category, which indicates a high economic value for public investment.

5. Conclusions of the cost-benefit analysis

- The project is not financially profitable, but it is clearly economically profitable, generating significant social and environmental benefits, which justify the use of non-reimbursable funds.

- With an EIRR of 7.6% and a positive net economic value of +€7.04 million, the investment offers a favorable cost-benefit ratio, demonstrating a solid value for money.

- The results are robust and in line with JASPERS' approaches to thermal rehabilitation projects in public buildings: significant investment, but with a positive economic impact and extensive social benefits.

- The additional benefits – reduction of local pollution, improvement of thermal comfort and quality of medical services – are qualitatively confirmed, even if they have not been quantified monetarily.

✅ Final result

Economic net present value (NPVₑn): +7.04 mln. EUR

Domestic Economic Rate of Return (EIRR): 7.6% → "Very good"

Cost-benefit analysis (CBA) – Case study 2

Project: Thermal rehabilitation of Teiuș Theoretical High School – Grades I–VIII (SMIS code 325436)

  - Purpose and objectives of the project

The project aims to improve the energy efficiency of the educational buildings within the Teiuș Theoretical High School – grades I–VIII, by reducing primary energy consumption, reducing greenhouse gas emissions and increasing the use of renewable energy sources. The interventions included thermal rehabilitation of the tyre, modernization of heating installations, installation of heat recovery systems and the use of passive technologies.

By implementing the project, the following are ensured:

- a reduction in primary energy consumption by approximately 65% compared to the initial situation (weighted average between the two bodies analyzed);

- a reduction in greenhouse gas emissions of around 78 tons of CO₂ per year, equivalent to an average decrease of more than 60%;

- an increase in overall energy efficiency and improvement of thermal comfort conditions for students and teachers.

2. Input data and working assumptions

| Element | Value/Assumption |
| --- | --- |
| Total project value | 3,961,579.21 lei ≈ 792,516 EUR (5 lei/EUR course) |
| Duration of analysis | 30 years |
| Discount rate | 3% |
| Initial Annual Primary Energy Consumption | 896.98 MWh/year |
| Annual primary energy consumption after renovation | 304.91 MWh/year |
| Reduction compared to the initial situation | −66.0% |
| Annual energy savings | ≈ 592 MWh/year |
| Initial GHG emissions (tons CO₂ equivalent /year) | 124.49 t/year |
| GHG emissions after renovation (tons CO₂ equivalent /year) | 46.53 t/year |
| Reduction of emissions compared to the initial | −62.7% |
| GHG emissions avoided annually (tons CO₂ equivalent /year) | ≈ 78 t/year |
| Renewable energy produced | ≈ 92 MWh/year (self-consumption) |
| Energy price | 120 EUR/MWh (EIB/JASPERS reference value) |

3. Methodological framework applied

The cost-benefit analysis was carried out according to the simplified JASPERS methodology for energy efficiency projects in buildings, with adaptations to the specifics of the projects implemented in the Centre Region.

The main methodological elements are:

- Costs include the total amount of the investment.

- The direct benefits were calculated on the basis of the annual primary energy savings, valued at a constant price of €120/MWh. An average price of €120/MWh, constant in real terms during the analysis, was used to assess the economic benefits. The value corresponds to the average reference level used in the economic analyses of the European Investment Bank (EIB) and in the JASPERS studies for energy efficiency projects, reflecting the full cost of energy (gas + electricity), without the temporary effect of capping schemes or subsidies applicable to residential consumers. This approach ensures the comparability of the results with other similar analyses at European level and a conservative estimation of the benefits, avoiding underestimating the value of energy savings in the context of the possible long-term increase in energy prices.

- The benefits of reducing CO₂ emissions are assessed by applying the European Investment Bank's (EIB) recommended benchmarks for the social cost of carbon (€165/t in 2025, progressively increasing to €800/t in 2050, thereafter kept constant).

- The indirect social benefits (thermal comfort, working conditions, health, educational environment, etc.) were estimated by applying a conservative multiplier coefficient of 1.0× to the value of the energy savings. This approach is aligned with the simplified practices recommended by JASPERS and the EC methodology for cost-benefit analysis (2014) and is frequently used in similar projects when specific data for monetization of social effects are lacking.

- The discount rate of 3% reflects the social benchmark used to assess public investment in the European Union. The 3% discount rate is in line with the recommendations of the European Commission (Guidance for the Cost-Benefit Analysis of Investment Projects, 2014) and the European Investment Bank (EIB, 2023) and is used as standard for the evaluation of public investments in the Member States of the European Union. This rate reflects the value of time and the social preference for current consumption, representing the reference level used in economic analyses for projects with non-reimbursable financing.

- The 30-year analysis period corresponds to the economic lifetime of investments in the energy renovation of buildings.

4. Results of the cost-benefit analysis

#### 4.1. Financial analysis

| Indicator | Value |
| --- | --- |
| Net present value (NPV_fin, 3%) | + €0.6 million |
| Internal Financial Rate of Return (FIRR) | ≈ 8.1% |

The financial analysis indicates that the project is attractive from the perspective of energy savings, with NPV_fin (3%) ≈ +0.60 mln. EUR and FIRR ≈ 8.1%. The non-reimbursable financing remains justified in order to accelerate the investment and to capture the social and environmental benefits that are not fully found in the beneficiary's financial flows.

#### 4.2. Economic analysis

Economic analysis includes, in addition to financial savings, positive social and environmental effects.

| Component | Updated value (mln. EUR) |
| --- | --- |
| Energy savings | 1,39 |
| Indirect social benefits (1.0×) | 1,39 |
| Reduction of CO₂ emissions (EIB cost of carbon) | 0,80 |
| Investment costs | −0.79 |
| Economic Net Present Value (NPV_econ) | +2.79 thousand. EUR |
| Internal Economic Rate of Return (EIRR) | ≈ 8.3% |

According to the JASPERS interpretation grid:

- ERR < 3,5% – slab

- 3.5–5% – acceptable

- 5–7% – good

- 7–10% – Very good

- >10% – excellent

The analyzed project falls into the "Very Good" category, confirming the economic viability and added value of the public investment.

5. Conclusions of the cost-benefit analysis

- The thermal rehabilitation project of the Teiuș Theoretical High School is viable both financially and economically, with an EIRR of 8.3% and a positive economic net worth of +EUR 2.79 million.

- The investment ensures consistent energy savings, a significant reduction in CO₂ emissions (≈ 78 t/year) and important social benefits for the community – improving thermal comfort, educational conditions and the quality of the local environment.

- The financial results (positive NPV_fin and FIRR ≈ 8.1%) confirm that the energy savings can fully cover the cost of the investment over the life of the project, which makes the intervention sustainable also from the perspective of the local budget.

- The economic analysis shows that the project offers value for money and contributes directly to the green transition objectives of the Centre Regional Programme, by reducing energy consumption and increasing the use of renewable sources.

✅ Final result

Economic Net Present Value (NPVₑn): +2.79 mln. EUR

Domestic Economic Rate of Return (EIRR): 8.3% → "Very Good"

Cost-benefit analysis (CBA) – Case study 3

Project: Thermal rehabilitation of 9 apartment blocks – Miercurea Ciuc Municipality

1. Purpose and objectives of the project

The project aims to increase the energy efficiency of apartment blocks in Miercurea Ciuc municipality, by reducing primary energy consumption and reducing greenhouse gas emissions, thus contributing to the green transition objectives and improving housing conditions for the population.

The planned interventions include complex thermal insulation works of the exterior walls, floors and bases, replacement of carpentry, application of thermal insulation solutions for facades and repair of the constructive elements related to the building envelope.

Through the implementation of the project, the following are ensured:

- An average reduction in primary energy consumption of around 43% compared to the initial situation;

- a reduction in greenhouse gas emissions of around 507 tCO₂ per year (−43% compared to baseline);

- a significant increase in thermal comfort and a reduction in maintenance costs for about 380 households.

2. Input data and working assumptions

| Element | Value/Assumption |
| --- | --- |
| Total project value | RON 19,734,701.76 ≈ EUR 3.95 million (course 5 lei/EUR) |
| Duration of analysis | 30 years |
| Discount rate | 3% |
| Initial Annual Primary Energy Consumption | 5,588.55 MWh/year |
| Annual primary energy consumption after renovation | 3,176.70 MWh/year |
| Reduction compared to the initial situation | −43.2% |
| Annual energy savings | ≈ 2,412 MWh/year |
| Initial GHG emissions (tons CO₂ equivalent /year) | ≈ 1,174 t/year |
| GHG emissions after renovation (tons CO₂ equivalent /year) | ≈,667 t/year |
| Reduction of emissions compared to the initial | −43.2% |
| GHG emissions avoided annually (tons CO₂ equivalent /year) | ≈ 507 t/year |
| Energy price | 120 EUR/MWh (EIB/JASPERS reference value) |

3. Methodological framework applied

The cost-benefit analysis was carried out according to the simplified JASPERS methodology for energy efficiency projects in residential buildings, with adaptations to the specifics of the implementation in the Centre Region.

The main methodological elements are:

- Costs include the total amount of the investment.

- The direct benefits were calculated on the basis of the annual primary energy savings, valued at a constant price of €120/MWh. An average price of €120/MWh, constant in real terms during the analysis, was used to assess the economic benefits. The value corresponds to the average reference level used in the economic analyses of the European Investment Bank (EIB) and in the JASPERS studies for energy efficiency projects, reflecting the full cost of energy (gas + electricity), without the temporary effect of capping schemes or subsidies applicable to residential consumers. This approach ensures the comparability of the results with other similar analyses at European level and a conservative estimation of the benefits, avoiding underestimating the value of energy savings in the context of the possible long-term increase in energy prices.

- The benefits of reducing CO₂ emissions are assessed by applying the European Investment Bank's (EIB) recommended benchmarks for the social cost of carbon (€165/t in 2025, progressively increasing to €800/t in 2050, thereafter kept constant).

- The indirect social benefits (thermal comfort, working conditions, health, educational environment, etc.) were estimated by applying a conservative multiplier coefficient of 1.0× to the value of the energy savings. This approach is aligned with the simplified practices recommended by JASPERS and the EC methodology for cost-benefit analysis (2014) and is frequently used in similar projects when specific data for monetization of social effects are lacking.

- The discount rate of 3% reflects the social benchmark used to assess public investment in the European Union. The 3% discount rate is in line with the recommendations of the European Commission (Guidance for the Cost-Benefit Analysis of Investment Projects, 2014) and the European Investment Bank (EIB, 2023) and is used as standard for the evaluation of public investments in the Member States of the European Union. This rate reflects the value of time and the social preference for current consumption, representing the reference level used in economic analyses for projects with non-reimbursable financing.

- The 30-year analysis period corresponds to the economic lifetime of investments in the energy renovation of buildings.

4. Results of the cost-benefit analysis

4.1. Financial analysis

| Indicator | Value |
| --- | --- |
| Net present value (NPV_fin, 3%) | +€1.72 million |
| Internal Financial Rate of Return (FIRR) | ≈ 8.9% |

The financial analysis indicates that the project is viable from the perspective of energy savings, with NPV_fin (3%) ≈ +1.72 mln. EUR and FIRR ≈ 8.9%.

Annual savings of approximately 2,412 MWh (equivalent to ~289,000 EUR/year) allow the investment to be recouped over the life of the project, making it financially sustainable.

4.2. Economic analysis

Economic analysis includes, in addition to financial savings, positive social and environmental effects.

| Component | Updated value (mln. EUR) |
| --- | --- |
| Energy savings | 5,67 |
| Indirect social benefits (1.0×) | 5,67 |
| Reduction of CO₂ emissions (EIB cost of carbon)** | 4,63 |
| Investment costs | −3.95 |
| Economic Net Present Value (NPV_econ) | +12.02 thousand. EUR |
| Internal Economic Rate of Return (EIRR) | ≈ 10.4% |

According to the JASPERS interpretation grid:

- ERR < 3,5% – slab

- 3.5–5% – acceptable

- 5–7% – good

- 7–10% – Very good

- >10% – excellent

The analyzed project falls into the "Excellent" category, confirming the high economic viability and social and environmental added value of public investment.

5. Conclusions of the cost-benefit analysis

- The thermal rehabilitation project of the nine apartment blocks in Miercurea Ciuc is both financially and economically viable, with an EIRR of 10.4% and a positive economic net worth of +EUR 12.02 million.

- The investment brings significant energy savings, a significant reduction in CO₂ emissions (≈ 507 t/year) and considerable social benefits for the inhabitants of the 380 apartments, by reducing maintenance costs and improving thermal comfort.

- The financial results (positive NPV_fin and FIRR ≈ 8.9%) confirm the financial sustainability of the project, with the return on investment through energy savings over the lifetime.

- The economic analysis shows that the project offers value for money and directly contributes to achieving the energy efficiency and emission reduction objectives of the Centre Regional Programme 2021–2027.

✅ Final result

Economic Net Present Value (NPVₑn): +12.02 mln. EUR

Internal Economic Rate of Return (EIRR): 10.4% → "Excellent"

Cost-benefit analysis (CBA) – Program-level intervention

Intervention: Energy efficiency of buildings – Centre Regional Programme 2021–2027

1. Purpose and objectives of the intervention

The intervention aims to support the transition to a low-carbon economy in the Centre Region, by increasing the energy efficiency of public and residential buildings, reducing primary energy consumption and reducing greenhouse gas emissions. By implementing the intervention:

- an average reduction in primary energy consumption of around 52% is achieved at the level of the financed buildings;

- the level of greenhouse gas emissions is reduced;

- the thermal comfort conditions and quality of life for the urban population are improved;

- strengthening the region's energy resilience and contribution to the European Union's climate objectives.

2. Input data and working assumptions

| Element | Value/Assumption |
| --- | --- |
| Total Investment Value | 119.56 thousand. EUR |
| Duration of analysis | 30 years |
| Discount rate | 3% |
| Total primary consumption (base) | 36,708 MWh/year |
| Total primary consumption (2029 target) | 17,437 MWh/year |
| Total energy savings | 19,270 MWh/year |
| Initial GHG emissions (tCO₂/year) | 8,600 t/year |
| GHG emissions after renovation (tCO₂/year) | 6,050 t/year |
| Emission reduction according to RCR29 | −2.550 equivalent t CO2/year |
| Emission reduction estimated by evaluators (factor 0,20 t/MWh) | −3.854 equivalent tons CO2/year |
| Energy price | 120 EUR/MWh (EIB/JASPERS baseline) |
| Reference emission factor | 0.20 tCO₂/MWh |
| Social benefits multiplier | 1.0× value of energy savings |
| Investment calendar | 2025–2029 |

3. Methodological framework applied

The cost-benefit analysis was carried out according to the simplified JASPERS methodology for energy efficiency projects, applied at the aggregate level of the project portfolio in the Centre Region. The main methodological assumptions are:

- The costs include the total amount of non-reimbursable investment, EU and national budget, but do not include the costs of ineligible expenses.

- The direct benefits (energy savings) were assessed at a constant average price of €120/MWh, corresponding to the benchmark used in the European Investment Bank's (EIB) economic analyses and JASPERS guidelines.

- The climate benefits were estimated by applying the Social Carbon Cost (EIB) benchmarks: €165/t in 2025, increasing to €800/t in 2050, which has since been kept constant.

- Indirect social benefits (comfort, health, educational conditions) were assessed by applying a multiplier of 1.0× to the value of energy savings, according to simplified JASPERS practices and the EC Guide to Cost-Benefit Analysis (2014).

- The 3% discount rate is in line with the recommendations of the European Commission and the EIB, reflecting the social value of time and the preference for current consumption.

- The 30-year analysis period corresponds to the economic lifetime of investments in the energy renovation of buildings.

- Calendar effects (staging of investments and benefits) were introduced by applying a composite discount factor: 0.928 for investments and 0.900 for benefits, resulting from assumptions on the timing of implementation.

4. Results of the cost-benefit analysis

4.1. Financial analysis

| Indicator | Value |
| --- | --- |
| Net present value (NPV_fin, 3%) | −€70.1 million |
| Internal Financial Rate of Return (FIRR) | negative |

The financial analysis confirms that the intervention is not financially profitable, which is normal for public energy efficiency programmes. The energy savings achieved cannot fully cover the investment costs in the absence of non-reimbursable support. However, the programme remains essential for achieving the green transition and decarbonisation objectives, fully justifying public funding.

#### 4.2. Economic analysis

Variants analyzed:

| Component | Updated value (mln. EUR) | V1 – Official (RCR29 = 2.550 tCO₂/an) | V2 – Analytical (0.20 tCO₂/MWh → 3,854 tCO₂/year) |
| --- | --- | --- | --- |
| Energy savings | 40,8 | 40,8 | 40,8 |
| Indirect social benefits (1.0×) | 40,8 | 40,8 | 40,8 |
| Reduction of CO₂ emissions (EIB cost of carbon) | – | 21,7 | 32,8 |
| Investment costs | – | −110.9 | −110.9 |
| Economic Net Present Value (NPVₑn) | – | −7.6 thousand. EUR | +3.4 thousand. EUR |
| Internal Economic Rate of Return (EIRR) | – | ≈ 3.0% | ≈ 3.6% |
| JASPERS | – | "Weap" (<3.5%) | "Acceptable" (3.5–5%) |

5. Conclusions of the cost-benefit analysis

- At the level of the program, investments in energy efficiency generate significant energy and social benefits, with a cumulative value of savings and social effects of over 81 mln. EUR.

- The programme is not financially self-sustainable, but it is economically justified, with the net benefits outweighing the costs when using a realistic emissions factor (0.20 tCO₂/MWh).

- The analysis confirms that the climate benefit has a decisive impact on the economic result: the use of the official target (RCR29 = 2,550 t/year) leads to a slightly negative NPV (−7.6 mln). EUR), while the application of a realistic emission factor turns the intervention into an economically viable one (NPVₑn = +3.4 mln. EUR, EIRR ≈ 3.6%).

- The intervention provides value for money, directly contributing to achieving the objectives of green transition, reducing emissions and increasing the energy efficiency of the built fund in the Centre Region.

- The results obtained are aligned with the JASPERS interpretation grid, where the EIRR between 3.5–5% is considered "acceptable", justifying the non-reimbursable support from European funds.

✅ Final result

- Official version (RCR29): NPVₑₙ = −7,6 mil. EUR | EIRR ≈ 3,0% („weak”)

- Analytical var. (factor 0.20 t/MWh): NPVₑn = +3.4 mln. EUR | EIRR ≈ 3.6% ("acceptable")

The analysis demonstrates that, although the intervention related to RSO2.1 is not financially profitable, it produces consistent social and environmental benefits, being economically justified and indispensable for the green transition at regional level.

COST-EFFICIENCYANALYSIS

The cost-efficiency analysis aims to assess the unit costs of the investments supported under the RSO2.1 intervention, by relating the total costs of the projects to the direct results achieved – i.e. the annual primary energy savings and the reduction of greenhouse gas emissions.

This analysis does not measure the financial return, but the efficiency of the use of public funds, showing how much, it costs to achieve a unit of result (1 MWh of energy saved or 1 ton’s CO₂ avoided). The calculated values are compared with national and European benchmarks (National Renovation Strategy, JASPERS methodology, technical-financial evaluation grid of projects), in order to assess the relative performance and economic efficiency of the interventions financed through the Centre Regional Programme

For the evaluation of the relative efficiency of the analyzed investments, three external benchmarks were used:

- The technical-financial evaluation grid applied to the projects submitted under the Centre Regional Programme, which differentiates the performance of the projects according to the cost-efficiency ratio, respectively the investment cost for 1 kWh/year of primary energy saved. The reference thresholds range from below €1,150/MWh/year (excellent performance) to above €3,440/MWh/year (low performance).

- The National Long-Term Renovation Strategy (2020), based on which the evaluators calculated indicative average values of 1,324 EUR/MWh/year saved and 5,463 EUR/tons CO₂/year avoided, as benchmarks of economic efficiency for energy renovation interventions.

- The simplified JASPERS methodology for the cost-benefit analysis of energy efficiency projects in buildings, which indicates, for the hypothetical case study analysed in the document, indicative ranges of 1,645–2,100 EUR/MWh/year saved and ≈12,000 EUR/tons CO₂ avoided, values corresponding to a common investment efficiency at European level.

Based on these benchmarks, the values of the unit costs calculated for the three case studies – the "Dr. Gheorghe Preda" Psychiatric Hospital in Sibiu, the Teiuș Theoretical High School and the set of 9 apartment blocks in Miercurea Ciuc were compared.

| Project | Investment (EUR) | Energy savings (MWh/year) | Cost / MWh (EUR/MWh/an) | Avoided emissions (tCO₂/year) | Cost / tCO₂ (EUR/t/an) |
| --- | --- | --- | --- | --- | --- |
| Sibiu Psychiatric Hospital – C17 | 9.278.121 | 2.445 | ≈ 3,795 | 510,5 | ≈ 18,180 |
| Teiuș High School | 792.516 | 592 | ≈ 1,339 | 78 | ≈ 10,160 |
| Miercurea Ciuc (9 blocks) | 3.946.940 | 2.412 | ≈ 1,636 | 507 | ≈ 7,785 |

The Teiuș and Miercurea Ciuc projects  are in the high efficiency zone, with unit costs of ≈1,340 EUR/MWh/year and ≈1,640 EUR/MWh/year, respectively, i.e. in the high efficiency range of the ETF Grid, below the JASPERS reference range (1,645–2,100 EUR/MWh/year) and close to the value of 1,324 EUR/MWh/year related to the National Long-Term Renovation Strategy. These values indicate efficient investments, which optimize the cost-energy ratio saved and which, in the technical-financial grid of the program, are scored in the higher category.

By comparison, the Sibiu Psychiatric Hospital project (≈3,800 EUR/MWh/year) exceeds the upper threshold of the ETF grid (3.44o EUR/MWh/year) and the European and national benchmarks, positioning itself as an expensive investment from an energy point of view. However, this difference is justified by the specifics of medical buildings, characterized by high energy consumption, complex technical infrastructure and strict requirements for comfort and safety.

In terms of unit costs related to avoided CO₂ emissions, the projects in Teiuș (≈10,100 EUR/t/year) and Miercurea Ciuc (≈7,800 EUR/t/year) are below the JASPERS reference values (≈12,000 EUR/t/year) and slightly above the national average (≈5,400 EUR/t/year), which confirms their economic efficiency and good performance in terms of climate impact.

The Sibiu project (≈18,000 EUR/t/year) registers higher values but is comparable to other similar investments in health infrastructure, where initial costs are higher and energy savings are gradually achieved.

Conclusions

Compared to the European and national benchmarks, it is observed that the projects in the educational and residential field fall within the limits of very good efficiency, demonstrating an optimal use of financial resources in relation to the results obtained.

The project in the sanitary field, although less efficient from a cost-energy point of view, remains economically justified by the high social and functional impact, confirming the cost specificity of this type of investment.

Results of the survey applied to the applicants for funding

According to the PDF document attached separately.

Case studies

## General Aspect

Purpose and objectives of the case studies

The case studies were included in the evaluation methodology with the main purpose of investigating and illustrating, through concrete examples, the efficiency of project implementation and the mechanisms by which they generate effects. This has allowed for a detailed analysis of how projects are implemented and how they contribute to achieving the set objectives.

In addition, case studies have played a key role in highlighting the differences in approach and outcomes between projects targeting public buildings and those targeting residential buildings. These differences were analyzed in the context of the type of beneficiary, the characteristics of the buildings, the degree of involvement of decision-makers and the complexity of implementing energy efficiency measures.

Through the analyses carried out, the case studies provided relevant answers to all the evaluation questions, complementing the quantitative data with qualitative information, essential for understanding the context and the real impact.

Last but not least, the case studies contributed to a better visualization of the analyzed effects, overcoming the limit of figures and statistics. Thus, the evaluation has become more informative and accessible for beneficiaries and all stakeholders, providing a concrete picture of how interventions have an impact in the real world, where the effects are directly manifested on the communities and buildings concerned.

Selection of case studies

The selection of cases was proportional to the distribution of the number of projects contracted per action, respectively 1 case study for action 3.1 and 2 case studies for action 3.2. The selection was made in consultation with MA RP for the Central Region, based on the following proposed selection criteria:

- Coverage at county level: Projects from different counties;

- Project typology: Phased/Non-phased;

- Implementation status: Project with the highest progress in implementation /Project with problems in implementation;

- Typology of buildings: Public buildings in different domains / Residential buildings.

List of selected case studies:

- Case study no. 1: Action 3.2, Sibiu County - "Thermal rehabilitation of pavilion C17 – physiotherapy, child psychiatry, SMIS code 301784

- Case study no. 2: Action 3.2, phased project, Alba County - "Thermal rehabilitation of the Teiuș Theoretical High School - Grades I-VIII", SMIS code 325436.

- Case study no. 3: Action 3.1, phased project, Hargita county - "Thermal rehabilitation of apartment blocks in order to raise energy performance, 9 blocks of flats in Miercurea Ciuc, Harghita county", SMIS code 325468.

| # | Project | Coverage at county level | Project typology | Action | Implementation Status | Typology of buildings |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | "Thermal rehabilitation of pavilion C17 – physiotherapy, child psychiatry, SMIS code 301784 | Sibiu County | phaseless | 3.2 | In implementation | Publish |
| 2 | "Thermal rehabilitation of the Teiuș Theoretical High School - Grades I-VIII", SMIS code 325436. | Alba County | phased | 3.2 | In implementation | Publish |
| 3 | "Thermal rehabilitation of apartment blocks in order to increase energy performance, 9 blocks of flats in Miercurea Ciuc, Harghita County", SMIS code 325468. | Harghita County | phased | 3.1 | Completed | Residential |

Therefore, the selected case studies meet all the established selection criteria, demonstrating relevance and representativeness for the object of the evaluation.

Methodology used to carry out the case studies

Each case study includes the following data collection methods:

- Analysis of the project documentation (funding application, progress reports, etc.);

- Interview with the project officer from MA RP for the Central Region;

- Interview with the project manager;

- Survey conducted among the beneficiaries of funding;

- Field visit - visit to the financed investment objective.

## Case study no. 1: Thermal rehabilitation of pavilion C17 – physiotherapy, child psychiatry, SMIS code 301784

- OBJECT AND PURPOSE OF THE CASE STUDY

The case study provided relevant answers to all evaluation questions, complementing the quantitative data with qualitative information, essential for understanding the context and real impact.

- PRESENTATION OF THE PROJECT OBJECT OF THE STUDY

| Project name | Thermal rehabilitation of pavilion C17 – physiotherapy, child psychiatry within the DR. GE Psychiatric Hospital. PREY |
| --- | --- |
| SMIS Code | 301784 |
| Location | Building C17 is located in Sibiu, str. Dr. Dumitru Bagdazar, nr. 12, identified by CF no. 131356. The related land has a total area of 72,409 sqm. The building consists of two buildings, of which Building A (the object of the project) has a built area of 1,554.14 sqm and 7,770.28 sqm. The heated usable area is 6,281.9 sqm, and the heated volume is 20,102 m3. The building has a height regime S + GF + 3F + technical floor and a roof structure. Currently, it is used by two entities: the "Dr. Gh. Preda" Psychiatric Hospital Sibiu and the Sibiu County Emergency Clinical Hospital - Physiotherapy Department II. Building A houses medical spaces, salons, consultation rooms, administrative and recovery areas, distributed on all levels. Vertical access is provided by two stairs and three elevators. Although there are 4 ramps for people with disabilities, they are non-compliant. The building requires rehabilitation works for energy efficiency and compliance with accessibility and thermal comfort requirements. |
| Benefit | Sibiu County Council |
| Priority / Specific objective | Policy objective: A greener Europe Priority: P3. A region with environmentally friendly communities Specific objective: RSO2.1_Promovarea energy efficiency measures and reduction of greenhouse gas emissions Fund: European Regional Development Fund |
| Project call/ Operation | PRC/41/PRC_P3/OP2/RSO2.1/PRC_A24 Action 3.2 - Energy efficiency in public buildings |
| Implementation period (start/end) | May 2024 - September 2027 |
| Project budget | The total value of the project is 46,390,606.63 Lei, of which: - the value of non-reimbursable co-financing from the ERDF: 38,896,705.79 lei; - the value of the non-reimbursable co-financing from the national budget: 948,907.94 lei, - the value of the beneficiary's contribution: 915,216.61 Lei; - total ineligible value of the project, including ineligible VAT: 629,776.29 Lei |
| Project context | General context - Sibiu County: - Sibiu is an economically prosperous city, with a low unemployment rate (~1.5% in August 2023), due to the presence of foreign investment and industries such as machine building, clothing, food and school supplies. - Industrial development, although economically beneficial, has led to an increase in CO₂ emissions and energy consumption. Sibiu County recorded an increase in energy consumption of 12.4%. - The energy efficiency of buildings is considered a priority for both reducing costs and improving public health, including in public buildings and hospitals. Historical and functional context - "Dr. Gh. Preda" Psychiatric Hospital Sibiu: - The hospital has a history that begins in 1860, being the first settlement of this type in southeastern Europe. - Today, it is a multi-pavilion hospital with approx. 20 buildings and numerous wards for children and adults. - Building C17 - Building A, located on Street. Dr. Dumitru Bagdazar is one of the most important and is used by both the Psychiatric Hospital and the County Hospital for the Physiotherapy II department. One of the representative buildings in the patrimony of the Sibiu County Council is the C17 building - physiotherapy and child psychiatry, within the "Dr. Gh. Preda" Psychiatric Hospital Sibiu, located on Dr. Dumitru Bagdazar Street no. 12. Building A, with an unfolded area of 7,770 sqm and a usable area of 6,281.90 sqm, is used by two entities: the Psychiatric Hospital and the Sibiu County Emergency Clinical Hospital (Physiotherapy II). The building has a height regime S+GF+3, a reinforced concrete structure and a roof structure. Annual energy consumption is high (4,072,785.42 kWh) and CO₂ emissions reach 100.95 kg/m²/year. The current state indicates major deficiencies: partial insulation, degraded floors, lack of access for people with disabilities and lack of thermal comfort. |
| Project justification | Problems identified - Building C17 (Building A): - Developed area: 7,770 sqm, usable area: 6,281.90 sqm. - Annual primary energy consumption: 4,072,785.42 kWh/year, with CO₂ emissions of 100.95 kg/m²/year. - The building has partial insulation, inadequate heating/cooling installations, poor lighting and lack of ventilation and air conditioning systems. - Access for people with disabilities is not properly ensured. - It does not provide thermal comfort for staff and patients. The reason for energy rehabilitation: - Rehabilitation is necessary to reduce high energy consumption (heating, hot water, lighting, ventilation), improve health conditions and achieve European and national energy efficiency targets. - The building is used around the clock (24/7), which makes investments even more urgent. The project is complementary to 5 other projects successfully completed by the Sibiu County Council in the field of health and energy efficiency. |
| Description of the investment | Building C17, PHYSIOTHERAPY PAVILION has a height regime (S+GF+3E), with a built area on the ground of 1554.14 sqm; the unfolded area of 4662.42 sqm; Building A is attached to Building B by a closed hallway without windows, buildings A and B being structurally and functionally independent. General information about the building: - Function: Hospital Unit (Physiotherapy and Paediatric Psychiatry) - Year built: 1980 - Height regime: S + P + 3E - Built area on the ground: 1,554.14 sqm - Unfolded area: 4,662.42 sqm - Total usable area: 6,281.9 sqm - Strength structure: Reinforced concrete frames and floors - Degree of seismic risk: RS III (according to technical expertise) - Existing heating: Centralized through the hospital network (cast iron and sheet metal radiators) - Domestic hot water source: Electric boiler - Historical monument building: No - Protected area: No The building is permanently occupied and served by three closed staircases and three elevators (including stretcher elevators). It is attached by a closed hallway to Building B but is structurally and functionally independent. |

- Objectives and Logic of the intervention

Purpose of the project and alignment with the objectives of RSO2.1

The general objective of the project "Thermal rehabilitation of pavilion C17 - Physiotherapy, Child Psychiatry", within the "Dr. Gheorghe Preda" Clinical Psychiatric Hospital Sibiu, is to promote energy efficiency and reduce greenhouse gas emissions in the public infrastructure owned by the Sibiu County Council.

The project aims to:

- supporting energy efficiency and the use of renewable energy in public buildings;

- promoting smart energy management;

- reducing energy consumption and, implicitly, maintenance costs for public institutions;

- improving the quality of the environment and combating climate change by decreasing CO₂ emissions.

This intervention is in line with the strategic objectives of the European Union, national, regional and county, in particular in the context of:

- the European Green Deal, which aims for climate neutrality by 2050;

- the target of reducing GHG emissions by 55% by 2030;

- and the New European Bauhaus initiative, which promotes sustainable, aesthetic and inclusive solutions for living and working spaces.

The project aims to achieve the following specific objectives:

- Increasing the energy efficiency of building C17, with an area of 6,281.9 sqm, by:

  - reduction of primary energy consumption by 60.15% compared to the situation before the renovation;

  - reducing annual greenhouse gas emissions by 80.52%.

- In-depth renovation of the public building by:

  - the application of a set of integrated measures for energy efficiency;

  - increasing the share of energy produced from renewable sources (solar and photovoltaic panels);

  - modernization of facilities and introduction of an automated energy consumption control system (BMS - Building Management System).

Alignment with strategic documents:

The project aligns and contributes to the achievement of the objectives formulated in:

- Centre Regional Development Plan 2021-2027, in particular under Strategic Area 4 - Environment, Energy Efficiency and Climate Change, which outlines:

  - the need to increase the share of renewable energy to 32% by 2030;

  - improving energy efficiency by at least 32.5%;

  - reduction of GHG emissions by 43% compared to 1990 levels.

- Priority 3, SO 2.1, Action 3.2. - Energy efficiency in public and residential buildings, within the "Centre Region" Programme:

  - The project fully meets the requirements of this action through the in-depth renovation of a public building, in order to increase energy performance.

Measure to adapt the intervention to the specifics of the building concerned

The degree of wear and tear of public buildings in Alba County is increased, and the need for renovation and energy efficiency is very high. The objectives and conditions of the funding line are considered relevant and correctly formulated, but the level of financial allocations is insufficient to cover the real need, which is much higher. In this context, the Alba County Council has prioritized the buildings that need complex thermal renovation and rehabilitation measures, the "Dr. Gh. Preda" Psychiatric Hospital in Sibiu being one of them.

The intervention proposed by the project was rigorously adapted to the functional, technical and operational specifics of Pavilion C17, part of the "Dr. Gh. Preda" Psychiatric Hospital in Sibiu, a medical unit with continuous use (24/7), dedicated to the pediatric physiotherapy and psychiatry departments.

The building is over 40 years old, has a high degree of wear and tear of construction elements and installations, and its functionality requires high standards in terms of thermal comfort, indoor air quality and operational safety. These characteristics were essential in the process of selecting and dimensioning the proposed measures, in line with the objectives of Priority 3 of the Centre Regional Programme: increasing energy efficiency, using renewable sources and improving conditions in public infrastructure.

Based on the energy audit and technical expertise, high-efficiency technological solutions were chosen, adapted to the non-stop operation regime of a health unit:

- All-new mechanical ventilation system with heat recovery, essential for medical building;

- Integrated heating/cooling system, with heat pumps, 550 kW chiller, 700 kW thermal module and fan coils;

- BMS (Building Management System) system for centralized monitoring and control of comfort and safety parameters (temperature, lighting, ventilation, fire);

- Solar and photovoltaic panels to partially ensure energy consumption from renewable sources;

- Thermal envelope works (façade insulation, high-performance carpentry, roof restoration, floor thermal insulation);

- Complete replacement of the electrical and lighting installations, using efficient LED fixtures;

- Accessibility of the building for people with disabilities, through ramps, railings and specific information panels.

The interventions were correlated with the specific norms of medical buildings, taking into account functional flows, patient safety and the need for a stable indoor microclimate.

In addition, the works were based on the experience gained by the Sibiu County Council in similar projects carried out through the ROP 2014–2020, this project being complementary to 5 other projects completed in the field of health and energy efficiency.

Thus, the intervention responds in a direct and efficient way to the specifics of the C17 Pavilion building, maximizing the impact of the investment on the energy efficiency and quality of the health infrastructure in Sibiu County.

- PROJECT COMPONENTS

| Activities | Activities carried out before signing the financing contract A1. Preparation of the technical and economic documentation of the DALI phase related to the project 1.1 Obtaining the urban planning certificate and the approvals required by it at the DALI phase Contracting services for the preparation of technical and economic documentation related to the project at the DALI phase Preparation of the technical-economic documentation at the DALI phase A2. Preparation of the financing file and its submission 2.1 Preparation of the project file and its submission 3. Signing the financing contract 3.1 Signing of the financing contract Activities carried out after signing the financing contract 4. Project management, monitoring and reporting within the project 4.1 Project management 4.2 Reporting within the project 4.3 Preparation of requests for payment/reimbursement of expenses project 4.4 Contracting of training, working visit and cooperation services 4.5 Interregional cooperation with partner from the Republic of Moldova 5. Elaboration of the technical-economic documentation for the PT phase and technical assistance from the designer and execution of the works 5.1 Contracting the economic operator in order to carry out the technical project, ensuring the technical verification, providing technical assistance from the designer 5.2 Contracting the execution of works 5.3 Preparation of technical documentation in the PT phase 5.4 Provision of technical quality verification services for the technical project 5.5 Contracting OSH services 5.6 Provision of OSH services 5.7 Provision of technical assistance services during the execution of the works 5.8 Execution of energy efficiency works 5.9 Reception of thermal rehabilitation works 6. Information and publicity within the project 6.1 Contracting the economic operator for the provision of information and advertising services 6.2 Provision of information and advertising services 7. Project auditing 7.1 Contracting the economic operator for the provision of project audit services 7.2 Provision of project audit services 8. Obtaining the Building Permit 8.1 Obtaining the necessary approvals and agreements for the issuance of the Building Permit 8.2 Obtaining the Building Permit 9. Supervision of execution works 9.1 Contracting of works supervision services 9.2 Provision of works supervision services |
| --- | --- |
| Expected results | Expected results from the implementation of the project: - Public building area with improved energy performance: 6,281.9 m2 usable area; - Annual specific final energy consumption for heating: 39.13 kwh/m2/year; - Estimated greenhouse gas emissions at the end of the investment: 19.66 kg CO2/m2/year; - Annual primary energy consumption: 258.34 kwh/m2/year. |

Brief description of the objectives of the investment and the work:

Investment objectives:

- Decrease in annual primary energy consumption

- Increasing the energy performance of the building

- Reducing CO₂ emissions

- Increasing comfort for patients and staff

- Promoting the use of renewable energy sources

Types of proposed work:

I. Basic measures – Increasing energy efficiency:

ARCHITECTURE:

- Facade thermosystem application

- Interventions at the base

- Exterior joinery replacement

- Roofing restoration

- Floor thermal insulation over the top level

INSTALLATIONS:

- Complete replacement of the heating system

- Execution of a new mechanical ventilation system

- LED Lighting Installation Replacement

- Mounting of:

  - Solar panels (18 pcs.)

  - Photovoltaic panels (total power 455 kW)

  - Floor-standing fan coils

  - 700 kW thermal module

  - 550 kW chiller

  - BMS Automatic Control System (Building Management System)

II. Auxiliary measures – Functionally correlated with the basic ones:

- Landscaping (sidewalks, ramps, railings)

- Excavations and interventions at foundations

- Masonry reinforcements and repairs

- Architectural renovations and restorations (including interior carpentry)

- Floor and finish restoration

- Installation of information boards for people with disabilities

III. Other eligible expenses:

- Technical design and engineering

- Technical Support

- Information and publicity activities

- Financial audit

- Miscellaneous and unforeseen, odds, commissions, etc.

Ineligible expenses:

- Electric vehicle charging station with 2 charging points

Technological and control aspects:

The project includes a computerized BMS system that will allow real-time monitoring and control of all mechanical and electrical installations: ventilation, heating/cooling, lighting, fire and security.

- PROGRESS IN IMPLEMENTATION

Progress towards objectives (indicators – planned/achieved targets)

| Categories | Indicator | Target | Done |
| --- | --- | --- | --- |
| Achievement indicators (program) | Public RCO19_Buildings with improved energy performance (square meters) | 6,281,900 square meters | - |
| Result indicators (programme) | RCR29_Emissions of estimated greenhouse gases (tons CO2 equivalent/year) | 123,500 tons CO2 equivalent/ year | - |
|  | annual primary energy RCR26_Consum (of which: of homes, public buildings, enterprises, etc.) (MWh/year) | 1,622.860 MWh/year | - |
| Additional achievement indicators | NA | NA | NA |
| Additional result indicators | Specific annual final energy consumption for heating (kwh/m2/year) | 39,130 kWh/m2/year | - |

Project achievements and results

| Project activities and sub-activities | Degree of achievement |  |
| --- | --- | --- |
|  | Complete | Partial % |
| Activities carried out before signing the financing contract |  |  |
| A1. Preparation of the technical-economic documentation phase DALI related to the project | 100% |  |
| 1.1 Obtaining the urban planning certificate and approvals requested by it at the DALI phase | 100% |  |
| Contracting services for the preparation of the technical and economic documentation related to the project at the DALI phase | 100% |  |
| Preparation of the technical-economic documentation at the DALI phase | 100% |  |
| A2. Preparation of the financing file and its submission | 100% |  |
| 2.1 Preparation of the project file and its submission | 100% |  |
| 3. Signing the financing contract | 100% |  |
| 3.1 Signing of the financing contract | 100% |  |
| Activities carried out after signing the financing contract |  |  |
| 4. Project management, monitoring and reporting within the project |  | 4% |
| 4.1 Project management |  | 12% |
| 4.2 Reporting on the project |  | 8% |
| 4.3 Preparation of requests for payment/reimbursement of expenses project |  | 0% |
| 4.4 Contracting of training, working visit and cooperation services |  | 0% |
| 4.5 Interregional cooperation with partner from the Republic of Moldova |  | 0% |
| 5. Elaboration of the technical-economic documentation for the PT phase and technical assistance from the designer and execution of the works |  | 30% |
| 5.1 Contracting the economic operator in order to carry out the technical project, ensuring the technical verification, providing technical assistance from the designer | 100% |  |
| 5.2 Contracting the execution of works |  | 0% |
| 5.3 Preparation of technical documentation in the PT phase |  | 40% |
| 5.4 Provision of technical quality verification services for the technical project |  | 30% |
| 5.5 Contracting OSH services | 100% |  |
| 5.6 Provision of OSH services |  | 0% |
| 5.7 Provision of technical assistance services during the execution of the works |  | 0% |
| 5.8 Execution of energy efficiency works |  | 0% |
| 5.9 Reception of thermal rehabilitation works |  | 0% |
| 6. Information and publicity within the project |  | 55% |
| 6.1 Contracting the economic operator for the provision of information and advertising services | 100% |  |
| 6.2 Provision of information and advertising services |  | 10% |
| 7. Project auditing |  | 50% |
| 7.1 Contracting of the economic operator for Provision of project audit services | 100% |  |
| 7.2 Provision of project audit services |  | 0% |
| 8. Obtaining the Building Permit |  | 65% |
| 8.1 Obtaining the necessary approvals and agreements for the issuance of the Building Permit | 100% |  |
| 8.2 Obtaining the Building Permit |  | 30% |
| 9. Supervision of execution works |  | 50% |
| 9.1 Contracting of works supervision services | 100% |  |
| 9.2 Provision of works supervision services |  | 0% |

Representative images of the investment objective:

Source: CJ Sibiu

The extent to which the project meets the needs of the target groups and socio-economic challenges

Main target groups

- Direct beneficiaries:

  - 1,643 patients treated annually in the pediatric psychiatry department of the "Dr. Gh. Preda" Clinical Psychiatric Hospital Sibiu

  - 115 employees (medical and auxiliary staff) of the child psychiatry department

  - 671 patients/year of the Physiotherapy II department of the Sibiu County Emergency Clinical Hospital (data for 2022)

  - 41 employees of the Physiotherapy II department

  - Sibiu County Council, as owner, by reducing the costs related to the maintenance, operation and current repairs of the building

- Indirect beneficiaries:

  - 147,245 inhabitants of Sibiu (source: INS)

  - 397,322 inhabitants of Sibiu County (source: INS)

  - Residents of neighboring counties, who can benefit from medical services offered in the rehabilitated building

  - Students of the "Victor Papilian" Faculty of Medicine in Sibiu, who carry out their training activity in the targeted medical units

  - Resident physicians and trainees

  - Families of direct beneficiaries, who will indirectly benefit from improved hospitalization and treatment conditions

- IMPLEMENTATION PROCESS

Obstacles identified:

- The implementation of works in functional medical buildings (hospitals that operate 24/7) has generated major difficulties in planning, logistics and safety, requiring phased works and the adaptation of internal flows.

- The limitations on the eligibility of auxiliary expenses (15% ceiling) restricted the possibility of covering essential related works (special installations, medical partitions, finishes in accordance with sanitary norms).

- Price fluctuations and a lack of procedural flexibility have led to budgetary pressures and the need to identify complementary sources of financing.

- The lack of real simplification of administrative procedures from one programming period to the next, despite the experience gained, was perceived as a bureaucratic barrier.

Implemented solutions:

- Phased planning of the works, with the temporary isolation of some areas of the building, in order to maintain the medical activity in safe conditions.

- Ensuring co-financing and ineligible expenses through a mix of sources: bank loans, sponsorships and local partnerships (e.g. Sibiu City Hall, Transgaz).

- Use of internal expertise (construction and installation engineers from CJ Sibiu) to validate technical solutions and monitor execution.

- Strengthening the relationship with the Center RDA and active participation in the Monitoring Committee, in order to signal the need for flexibility in the implementation of complex projects.

Positive elements:

- The beneficiary has an experienced in-house team, capable of managing several complex projects simultaneously.

- The rehabilitation projects carried out previously (through ROP and PNRR) have provided a solid base of experience and standardized procedures.

- The efficient cooperation between the County Council, hospitals and designers facilitated the adaptation of interventions to medical specifics.

- The introduction of modern technologies (BMS systems, regenerative ventilation, photovoltaic panels) ensured the relevance and sustainability of investment.

- ESTIMATED impact

- Public building area with improved energy performance: 6,281.9 m2 usable area

- Specific annual final energy consumption for heating: 39.13 kwh/m2/year

- Estimated greenhouse gas emissions at the end of the investment: 19.66 kg CO2/m2/year

- Annual primary energy consumption: 258.34 kwh/m2/year.

"We continue the investment projects in health infrastructure, but which also have a significant benefit on the environment. The energy efficiency of buildings is one of the most important topics addressed in the European Green Deal, which brings benefits to the community in the long term and will certainly contribute both to increasing the quality of the medical act, but also to the environment by reducing the consumption of greenhouse gases that have a direct impact on climate change. At the same time, the project will also have an impact from an economic point of view, as it contributes to a significant reduction in energy consumption." (CJ Sibiu)

- EFFICIENCY OF the intervention (cost-benefit analysis)

The cost-benefit analysis, carried out within the DALI documentation, confirmed the technical and economic viability of the investment, with a cost-efficiency ratio of 3.047.

The project contributes to an estimated 60.15% reduction in primary energy consumption and 80.52% reduction in CO₂ emissions, exceeding the efficiency thresholds required for a "thorough renovation".

The main benefits identified are:

- Significant budget savings by lowering energy costs for a building that operates around the clock;

- Improving comfort and safety conditions for patients and staff, with a direct impact on the quality of medical services;

- Reducing the carbon footprint and aligning with the objectives of the European Green Deal;

- Social added value, by creating a healthier and more efficient environment in the consumption of resources.

Compared to other similar projects in the region, the investment has high efficiency due to the combination of integrated technological solutions (heat pumps, fan coils, BMS, solar and photovoltaic panels), but also due to the rigorous planning of the execution in an active medical environment.

- Lessons learned and best practices

Factors that favored success:

- The experience gained by the Sibiu County Council in energy efficiency and public health projects.

- Integrated coordination of all project stages (from energy audit to execution), with the direct involvement of internal specialists.

- Effective collaboration with partner institutions (hospitals, local authorities, sponsors).

- Phased implementation and permanent adaptation to the operational requirements of medical units.

- Application of sustainable design principles and integration of green technologies (BMS, photovoltaic panels, regenerative ventilation).

Barriers and challenges:

- Lack of correlation between funding sources and strict eligibility limits; difficulties in combining PNRR and PR Centre funds.

- The need for real simplification of administrative and reporting procedures for complex projects.

- Underestimating the time needed for work in functional buildings.

- Limiting the ceiling for ancillary expenses to 15%, insufficient for medical buildings with special technical requirements.

Replicable recommendations and best practices:

- Introducing a more flexible margin for related expenditure in the case of medical infrastructure.

- Capitalizing on the internal expertise (technical and financial) of the large beneficiaries, through mixed implementation teams.

- Strengthening the dialogue between RDA and beneficiaries through regular thematic consultations.

- Promoting European technical cooperation (visits, partnerships, exchange of experience) for the transfer of know-how in the field of energy efficiency.

- CONCLUSIONS

The project is part of a broader approach carried out by the Sibiu County Council, aiming at energy transition and sustainability in the public sector. The rehabilitation of pavilion C17, which mainly serves the sections for children, is the fifth investment, along with the rehabilitation of the Central Pavilion and pavilions C8 and C16, as well as the building where the thermal point operates.

This investment is complementary to other projects already implemented by the Sibiu County Council, within which modern systems for the production of energy from renewable sources have been installed. The current project actively contributes to energy efficiency goals by:

- implementing specific measures to reduce energy consumption;

- expanding the use of renewable energy;

- encouraging the use of environmentally friendly materials and products.

In the design stage, special attention was paid to complying with urban planning regulations and ensuring a harmonious integration into the existing built complex. The architectural interventions aim not only at energy efficiency, but also at improving the visual appearance of the building, contributing to the aesthetic regeneration of the area and the architectural coherence of the hospital complex.

The investment responds to a real public need, having a direct impact on the quality of medical services offered to patients. The project is also aligned with the participatory initiatives carried out over time, involving the local community in the decision-making process and strengthening trust in the actions of the public administration.

## Case study no. 2: Thermal rehabilitation Teiuș Theoretical High School - Grades I-VIII, SMIS code 325436

Source: Teiuș Theoretical High School (before and after thermal rehabilitation)

- OBJECT AND PURPOSE OF THE CASE STUDY

The case study provided relevant answers to all evaluation questions, complementing the quantitative data with qualitative information, essential for understanding the context and real impact.

- PRESENTATION OF THE PROJECT OBJECT OF THE STUDY

| Project name | Thermal rehabilitation Teiuș Theoretical High School - Grades I-VIII |
| --- | --- |
| SMIS Code | 325436 |
| Location | Region 7 Centre, Alba County, Teiuș City, Decebal Street, no. 49 |
| Benefit | UAT CITY TEIUŞ |
| Priority / Specific objective | Policy objective: A greener Europe Priority: P3. A region with environmentally friendly communities Specific objective: RSO2.1_Promovarea energy efficiency measures and reduction of greenhouse gas emissions Fund: European Regional Development Fund |
| Project call/ Operation | PRC/340/PRC_P3/OP2/RSO2.1/PRC_A24 Action 3.2 - Energy efficiency in public buildings |
| Implementation period (start/end) | 11.07.2024 - 11.01.2026 The project implementation period was extended by 12 months by the addendum approved on 20.12.2024 |
| Project budget | The total value of the project is 3,961,579.21 Lei, of which: - the value of the non-reimbursable co-financing from the ERDF: 2,487,236.91 lei; - the value of the non-reimbursable co-financing from the national budget: 438,924.16 lei, - the value of the beneficiary's contribution: 59,717.59 lei; - total ineligible value of the project, including ineligible VAT: 975,700.55 Lei |
| Project context | The buildings of the Teiuș Theoretical High School (grades I-VIII) register a high energy consumption, with no efficiency investments being made in the last 5 years. In Romania, educational buildings are the largest consumers in the public sector, and their efficiency is a priority at European and national level. The project responds to the commitments made through the Sustainable Energy Action Plan of the city of Teiuș and the county strategies on reducing CO₂ emissions, promoting the use of renewable sources and the modernization of educational infrastructure. |
| Project justification | The buildings of the Teiuș Theoretical High School (grades I-VIII) have a high level of energy consumption and have not benefited from thermal rehabilitation works in the last 5 years, despite the fact that they serve 451 students and 49 employees. According to 2016 data, electricity and natural gas costs exceed 79,000 lei annually, which indicates a low energy performance and a significant financial burden for the local budget. Nationwide, educational buildings account for approximately 26% of non-residential energy consumption, recording the highest consumption values (≈354 kWh/m²/year). In this context, investments in the energy efficiency of educational infrastructure are essential to reduce consumption, greenhouse gas emissions and operating costs, while contributing to increasing the quality of education and improving learning conditions. The project is aligned with the European and national objectives on green transition and energy efficiency, assumed through relevant strategies and documents: - The European Green Deal and the EU 2030 climate and energy targets, - Sustainable Energy Action Plan of the city of Teiuș (20% reduction of CO₂ emissions), - Alba County Development Strategy and Intercommunity Plans (AIDA, Alba de Jos), which promote energy efficiency in public buildings and the use of renewable resources. In addition, the project responds to local social and demographic needs. Education is a strategic factor for the sustainable development of the community, and the improvement of school infrastructure supports the training of the future workforce, the reduction of unemployment and the increase of the quality of life. The existence of a safe, modern and energy-efficient educational environment will have direct positive effects on school performance and student engagement. |
| Description of the investment | Main works included: - Thermal rehabilitation of buildings: insulation of facades, floors, change of exterior carpentry. - Modernization of heating and hot water systems: thermal networks, central heating units, heating bodies. - Installation of renewable energy sources: ground/water heat pumps with a minimum power of 42.60 kW each. - Improving air quality: hygro-adjustable grilles in classrooms and teachers. - Modernization of lighting installations: LED lighting fixtures. - Integrated energy management: thermal energy meters for monitoring consumption. - Technological equipment: functional equipment and machinery. Related works: - Repairs of facades, roof, sidewalks, interior finishes, plumbing and electrical installations. - Adaptations for access for people with disabilities. Building details: Building A (School grades I-IV): - Built in 1954, regime: S+GF+1 - Heated usable area: 1356.34 sqm - Occupancy: semi-permanent (12h/day, 5 days/week, 8 months/year) - It has no renewable energy sources - Not in a protected area - The work has not started Building B (School grades V-VIII): - Built in the 1970s, regime: GF+1 - Heated usable area: 1021.27 sqm - Occupancy: semi-permanent (similar to building A) - It has no renewable energy sources - Not in a protected area - The work started (started on 27.01.2021) Status of the works: - Building B and the heating plant building: completed and partially received. - Building A: execution in a proportion of about 73% on the date of submission of the application (31.12.2023: 66.38%) - Works performed: thermal insulation, carpentry, electrical and heating installations. Stage II: - Information and advertising (press releases, plaques, stickers) - Completion of the execution and acceptance of the works - Technical assistance (site supervision, consultancy) - Financial audit and energy certification of buildings - Acquisition of the equipment provided for the project |

- Objectives and Logic of the intervention

Purpose of the project and alignment with the objectives of RSO2.1

Project purpose: To improve the energy efficiency of the educational buildings within the Teiuș Theoretical High School - grades I-VIII through measures to save energy resources and reduce greenhouse gas emissions.

Specific objectives of the project:

- CORP A

- The decrease of the specific annual level of greenhouse gases (equivalent tons of CO2) from 61.19, the value recorded at the beginning of the project implementation to 19.66, the value that will be reached within a maximum of 58 months from the signing of the Financing Contract.

- The decrease in the annual primary energy consumption (kWh/year) from 575478.18, the value recorded at the beginning of the project implementation to 173321.39, the value that will be reached within a maximum of 58 months from the signing of the Financing Contract.

- The decrease in the annual final energy consumption in the public building (from non-renewable sources) (toe) from 49.82, the value recorded at the beginning of the project implementation to 14.90, the value that will be reached within a maximum of 58 months from the signing of the Financing Contract.

- The decrease in the total specific annual consumption of primary energy (from non-renewable sources) (kWh/m2/year) from 415.5, the value recorded at the beginning of the project implementation to 129.46, the value that will be reached within a maximum of 58 months from the signing of the Financing Contract.

- Decrease in the total specific annual consumption of primary energy (from non-renewable sources) (kWh/m2/year), of which for heating/cooling from 409.61, the value recorded at the beginning of the project implementation to 100.92, the value that will be reached within a maximum of 58 months from the signing of the Financing Contract.

- Increase of the total annual consumption of primary energy from renewable sources (kWh/year), from 0, the value recorded at the beginning of the project implementation to 46008, the value that will be reached within a maximum of 58 months from the signing of the Financing Contract.

- Increase of the total annual consumption of primary energy from renewable sources (kWh/year) of which for heating/cooling, from 0, the value recorded at the beginning of the project implementation to 46008, the value that will be reached within a maximum of 58 months from the signing of the Financing Contract.

- Production of energy from renewable sources over 10% by installing alternative sources of energy production as a result of the thermal rehabilitation of the building intended for education within the Teiuș Theoretical High School – grades I-VIII, within 58 months from the signing of the Financing Contract.

- The use of passive technologies and the installation of heating systems with heat recovery as a result of the thermal rehabilitation of the building intended for education within the Teiuș Theoretical High School – grades I-VIII within 58 months from the signing of the Financing Contract.

- CORP B

- The decrease of the specific annual level of greenhouse gases (equivalent to tons of CO2) from 63.30, the value recorded at the beginning of the project implementation to 26.87, the value that will be reached within a maximum of 58 months from the signing of the Financing Contract.

- Decrease of the annual primary energy consumption (kWh/year) from 321501.31, the value recorded at the beginning of the project implementation to 131589.63, the value that will be reached within a maximum of 58 months from the signing of the Financing Contract

- The decrease in the annual final energy consumption in the public building (from non-renewable sources) (toe) from 27.64, the value recorded at the beginning of the project implementation to 11.31, the value that will be reached within a maximum of 58 months from the signing of the Financing Contract.

- The decrease in the total specific annual consumption of primary energy (from non-renewable sources) (kWh/m2/year) from 314.8, the value recorded at the beginning of the project implementation to 130.2, the value that will be reached within a maximum of 58 months from the signing of the Financing Contract.

- Decrease in the total specific annual consumption of primary energy (from non-renewable sources) (kWh/m2/year), of which for heating/cooling from 308.78, the value recorded at the beginning of the project implementation to 100.92, a value that will be reached within a maximum of 58 months from the signing of the Financing Contract.

- Increase of the total annual consumption of primary energy from renewable sources (kWh/year), from 0, the value recorded at the beginning of the project implementation to 46008, the value that will be reached within a maximum of 58 months from the signing of the Financing Contract.

- Increase of the total annual consumption of primary energy from renewable sources (kWh/year) of which for heating/cooling, from 0, the value recorded at the beginning of the project implementation to 46008, the value that will be reached within a maximum of 58 months from the signing of the Financing Contract.

- Production of energy from renewable sources over 10% by installing alternative sources of energy production as a result of the thermal rehabilitation of the building intended for education within the Teiuș Theoretical High School – grades I-VIII, within 58 months from the signing of the Financing Contract.

- The use of passive technologies and the installation of heating systems with heat recovery as a result of the thermal rehabilitation of the building intended for education within the Teiuș Theoretical High School - grades I-VIII within 58 months from the signing of the Financing Contract.

Extent to which the intervention was adapted to the specifics of the building concerned

The analyzed project is part of a phased intervention, aiming at the complete renovation of the Theoretical High School in the locality. The first stage, financed by ROP 2014-2020, covered grades IX-XII, and the current stage (through the RP for the Central Region) targets classes I-VIII, in two distinct buildings.

The intervention was directly adapted to the technical and functional particularities of the two buildings of the Teiuș Theoretical High School - grades I-VIII, considering the age of the constructions (over 80 years), the educational destination and the high degree of wear of the installations.

The proposed technical solutions were selected on the basis of the energy audit and the expertise gained during the previous stage (rehabilitation of classes IX-XII), which served as a pilot project for testing the efficiency of the measures. High-efficiency technologies, such as ground/water heat pumps and photovoltaic panels, adapted to the size and consumption of each building body, were used. The project also integrated measures to improve ventilation (hygroadjustable grids) and optimize lighting, so that the educational spaces comply with thermal comfort and air quality standards.

The works were sized according to the height regime, the number of occupants and the daily duration of use, and accessibility for people with disabilities was included in the final design. Therefore, the intervention was adapted not only to the technical needs of the building, but also to the social and educational specificity of the beneficiaries.

The adaptation of the program to the needs of small towns has given UAT Teiuș the opportunity to prepare and submit funding applications in order to attract European funds, thus contributing to sustainable local development and improving public infrastructure.

In conclusion, the Intervention was designed taking into account the functional and technical particularities of the buildings, as well as their educational destination. The technical solutions were based on the energy audit and the experience gained in the previous stage of rehabilitation. The installation of ground/water heat pumps and photovoltaic panels was sized according to the energy needs of each body. Controlled ventilation measures, LED lighting and high-performance thermal insulation have been introduced, ensuring thermal comfort and air quality for students and staff. The final design also included accessibility solutions for people with disabilities.

- PROJECT COMPONENTS

| Activities | - Activity: 2. Carrying out building rehabilitation works - 2.1 Carrying out rehabilitation works in the pre-contractual period - Activity: 4. Providing technical assistance from the designer and the site supervisor - 4.1 Ensuring technical assistance from the designer and the site manager in the pre-contractual period - Activity: 6. Project Management - 6.1 Project monitoring at the pre-contractual stage - Activity: 9. Carrying out project audit activities - 9.1 Carrying out project audit activities during the pre-contractual period - Activity: 11. Conducting the final energy audit - 11.1 Final energy audit in the pre-contractual period - Activity: 8. Information and publicity - 8.2 Making and applying self-adhesive posters, temporary panels and permanent plates - 8.1 Making and publishing the announcement at the start of the project implementation - 8.3 Making and publishing a press announcement at the end of the project implementation - Activity: 1. Signing the financing contract - 1.1 Signing of the Financing Agreement - Activity: 3. Carrying out the rehabilitation works of the buildings - 3.1 Carrying out building rehabilitation works in the post-contractual stage - Activity: 5. Providing technical assistance from the designer and the site manager - 5.1 Providing technical assistance from the designer and site manager in the post-contractual period - Activity: 7. Project Management - 7.2 Preparation of progress reports and final project reports - 7.1 Project monitoring in the post-contractual period - 7.3 Preparation and submission of the payment/reimbursement request - Activity: 10. Carrying out project audit activities - 10.1 Carrying out project audit activities in the post-contractual period - Activity: 12. Conducting the final energy audit - 12.1 Final energy audit in the post-contractual period - Activity: 13. Submission of the request for reimbursement/final payment - 13.1 Submission of the request for reimbursement/final payment, including during the verification and reimbursement period of the amounts requested |
| --- | --- |
| Expected results | Building A - Annual specific level of greenhouse gases (equivalent tons of CO₂) reduced from 61.19, the value recorded at the beginning of the project implementation, to 19.66. - Annual primary energy consumption (kWh/year) reduced from 575,478.18, the value recorded at the beginning of the project implementation, to 173,321.39. - Annual final energy consumption in the public building (from non-renewable sources) (to be reduced from 49.82, the value recorded at the beginning of the project implementation, to 14.90. - Total specific annual consumption of primary energy (from non-renewable sources) (kWh/m²/year) from 415.5, the value recorded at the beginning of the project implementation, to 129.46. - Total specific annual consumption of primary energy (from non-renewable sources) (kWh/m²/year), of which for heating/cooling, reduced from 409.61, the value recorded at the beginning of the project implementation, to 100.92. - Total annual consumption of primary energy from renewable sources (kWh/year) increased, from 0, the value recorded at the beginning of the project implementation, to 46,008. - Total annual primary energy consumption from renewable sources (kWh/year), of which for heating/cooling, increased from 0, the value recorded at the beginning of the project implementation, to 46,008. - Building of the type of buildings intended for education within the Teiuș Theoretical High School – grades I-VIII, which produces energy from renewable sources in a percentage of over 10%, by installing alternative sources of energy production, as a result of thermal rehabilitation. - Building intended for education using passive technologies and installation of heating systems with heat recovery, as a result of thermal rehabilitation. Corp B - Annual specific level of greenhouse gases (equivalent tons of CO₂) reduced from 63.30, the value recorded at the beginning of the project implementation, to 26.87. - Annual primary energy consumption (kWh/year) reduced from 321,501.31, the value recorded at the beginning of the project implementation, to 131,589.63. - Annual final energy consumption in the public building (from non-renewable sources) (to) reduced from 27.64, the value recorded at the beginning of the project implementation, to 11.31. - Total specific annual consumption of primary energy (from non-renewable sources) (kWh/m²/year) from 314.8, the value recorded at the beginning of the project implementation, to 130.2. - Total specific annual consumption of primary energy (from non-renewable sources) (kWh/m²/year), of which for heating/cooling, reduced from 308.78, the value recorded at the beginning of the project implementation, to 100.92. - Total annual consumption of primary energy from renewable sources (kWh/year) increased, from 0, the value recorded at the beginning of the project implementation, to 46,008. - Total annual primary energy consumption from renewable sources (kWh/year), of which for heating/cooling, increased from 0, the value recorded at the beginning of the project implementation, to 46,008. - Building of the type of buildings intended for education within the Teiuș Theoretical High School – grades I-VIII, which produces energy from renewable sources in a percentage of over 10%, by installing alternative sources of energy production, as a result of thermal rehabilitation. - Building intended for education using passive technologies and installation of heating systems with heat recovery, as a result of thermal rehabilitation. - Decreasing the annual final energy consumption in public buildings (from non-renewable sources) by 51,250 to be, at the end of the project implementation. - Decrease in the total specific annual consumption of primary energy (from non-renewable sources) by 242.47 kWh/m²/year. - 2 buildings benefiting from measures to increase energy efficiency. - Decrease in the total specific annual consumption of primary energy (from non-renewable sources), of which for heating/cooling, by 265.74 kWh/m²/year. |

- PROGRESS IN IMPLEMENTATION

Progress towards objectives (indicators – planned/achieved targets)

| Categories | Indicator | Target | Done |
| --- | --- | --- | --- |
| Achievement indicators (program) | Public RCO19_Clădiri with improved energy performance (square meters) | 2,377.61 square meters | - |
| Result indicators (programme) | RCR29_Emisii of estimated greenhouse gases (tons CO2 equivalent/year) | 46,53 tons CO2 equivalent/ year | - |
|  | annual primary energy RCR26_Consum (of which: of homes, public buildings, enterprises, etc.) (MWh/year) | 304.91 MWh/year | - |

Achievements and results - illustrative examples

| Activity | Results | Percentage of achievement |
| --- | --- | --- |
| - Activity: 2. Carrying out building rehabilitation works - 2.1 Carrying out building rehabilitation works in the pre-contractual period | Carrying out the building rehabilitation works in the pre-contractual period | 100% |
| - Activity: 4. Providing technical assistance from the designer and the site supervisor - 4.1 Ensuring technical assistance from the designer and the site manager in the pre-contractual period | Providing technical assistance from the designer and the site manager during the pre-contractual period | 100% |
| - Activity: 6. Project Management - 6.1 Project monitoring at the pre-contractual stage | Project monitoring in the pre-contractual stage | 100% |
| - Activity: 9. Carrying out project audit activities - 9.1 Carrying out project audit activities during the pre-contractual period | Carrying out project audit activities during the pre-contractual period | 100% |
| - Activity: 11. Conducting the final energy audit - 11.1 Final energy audit in the pre-contractual period | Energy certification of the building in the pre-contractual stage | 100% |
| - Activity: 8. Information and publicity - 8.1 Making and publishing the announcement at the start of the project implementation - 8.2 Making and applying self-adhesive posters, temporary panels and permanent plates - 8.3 Making and publishing a press announcement at the end of the project implementation | 8.2. – 8.1. The announcement of the start of the project for phase II has been published on the beneficiary's website 8.3. – | 0% 100% 0% |
| - Activity: 1. Signing the financing contract - 1.1 Signing of the Financing Agreement | Signing of the Financing Agreement | 100% |
| - Activity: 3. Carrying out the rehabilitation works of the buildings - 3.1 Carrying out building rehabilitation works in the post-contractual stage | Extension of the period of execution of the works Emergence of site provisions with additional works | 58% |
| - Activity: 5. Providing technical assistance from the designer and the site manager - 5.1 Providing technical assistance from the designer and site manager in the post-contractual period | Providing technical assistance from the designer and the site manager | 58% |
| - Activity: 7. Project Management - 7.2 Preparation of progress reports and final project reports - 7.1 Project monitoring in the post-contractual period - 7.3 Preparation and submission of the payment/reimbursement request | 7.2. Monitoring of the project in the post-contractual phase 7.1. Preparation of progress reports 7.3. 2 Refund Requests Submitted | 66% 66% 50% |
| - Activity: 10. Carrying out project audit activities - 10.1 Carrying out project audit activities in the post-contractual period | Carrying out project audit activities | 50% |
| - Activity: 12. Conducting the final energy audit - 12.1 Final energy audit in the post-contractual period | - | 0% |
| - Activity: 13. Submission of the request for reimbursement/final payment - 13.1 Submission of the request for reimbursement/final payment, including during the verification and reimbursement period of the amounts requested | - | 0% |

03.02.2024, the Teiuș City Hall presented the status of the thermal rehabilitation works at the Theoretical High School in the city. The new boilers are installed that will provide the heating agent and hot water until they are coupled with the new NIBE heat pumps. The heating system of the high school will allow, together with the thermal rehabilitation works on the building bodies, the reduction of methane gas consumption by over 30% (Teiuș City Hall).

The extent to which the project meets the needs of the target groups and socio-economic challenges

The main target groups targeted by the project:

- Direct beneficiaries of the project

  - The project has as direct beneficiaries the Teiuș Theoretical High School – grades I-VIII and the Administrative-Territorial Unit (UAT) Teiuș:

a) The school, with 451 students and 49 employees, will benefit from investments in the three buildings, aiming at energy efficiency, the use of energy from renewable sources and the creation of an adequate educational environment.

b) UAT Teiuș is a beneficiary by owning and managing these buildings and by the project's contribution to the local objective of reducing CO2 emissions by 20% by 2020. At the same time, the investments will reduce City Hall's expenses with utilities, supporting the transformation of buildings into energy efficiency models.

- Indirect beneficiaries of the project

  - Another beneficiary of the project is the local community in the city of Teiuș, which will benefit from the use of modern technologies that produce energy from renewable sources. These measures contribute to sustainable development, reducing the negative impact on the environment and improving the quality of life of the inhabitants.

- IMPLEMENTATION PROCESS

Main obstacle:

- Increasing costs of construction materials and labor in the post-pandemic period.

- Difficulties generated by the administrative transition between the programming periods (ROP and PR Centre).

- The need to adjust financial flows for ongoing works.

- Punctual coordination difficulties between designer and builder.

Solutions adopted:

- Using a bank loan as a bridge mechanism and to cover ineligible expenses.

- Careful monitoring of the execution and close collaboration between the city hall, designer and builder.

- Phased planning of the works and adjustment of the execution schedule according to resources.
The active involvement of the local management team and the constant support of RDA Centre.

Positive elements:

- Experience gained in previous rehabilitation projects

- Effective collaboration with consulting firms and quick adaptation to program requirements.

- Community acceptance and support of teachers.

- Visible results in increasing comfort and reducing energy consumption.

- ESTIMATED impact

- Decrease in the annual primary energy consumption of public buildings – 304.91 Kwh/year.

- Greenhouse gas reduction – estimated annual decrease: 46.53 tons of CO2.

- EFFICIENCY OF the intervention (cost-benefit analysis)

The cost-benefit analysis was carried out by an external consultant, independent of the designer, and demonstrated the economic and energy viability of the investment. The cost-benefit ratio showed a positive return on investment, with an estimated payback period of around 8-10 years, due to reduced energy consumption and maintenance costs. Compared to the previous project (phase I - ROP 2014-2020), the current investment registers an increased efficiency by integrating NIBE heat pumps and LED systems with intelligent control. By decreasing primary energy consumption by more than 45% and reducing CO₂ emissions by more than 40 tons annually, the project demonstrates a judicious use of public resources, providing long-term benefits to the community and the environment.

- Lessons learned and best practices

- The phasing of the work allowed learning from previous experiences and the application of optimized solutions.

- The constant collaboration with the Centre RDA has facilitated the avoidance of administrative blockages.

- The use of high-efficiency green technologies (heat pumps, LEDs, high-performance insulation) has generated sustainable results.

- Transparent communication with the local community has contributed to the acceptance of the project and increased visibility.

- Prudent financial planning and the use of bridge loans ensured the continuity of implementation.

- CONCLUSIONS

- Better linkage between the transition periods of funding programmes is needed to avoid administrative disruptions.

- Greater flexibility in adjusting budgets to price increases and introducing indexation mechanisms is recommended.

- For similar projects, it is useful to prepare the technical-economic documentation in advance and to provide a reserve fund for unforeseen works.

- The Teiuș experience can be replicated in other small localities, demonstrating that investments in energy efficiency are feasible and sustainable even for UATs with limited resources.

Thus, the energy efficiency project at the Teiuș Theoretical High School demonstrates how a small local administration can efficiently manage complex projects, through rigorous planning and institutional cooperation. The intervention was tailored to the specific needs of the educational infrastructure and effectively combined technical, social and environmental objectives. The significant reduction in energy consumption and CO₂ emissions confirms the real impact of the investment on local sustainability. The Teiuș case can be considered a replicable example for other UATs in the region, demonstrating that energy efficiency represents a strategic investment in the quality of life and in the development of communities. For the future, it is recommended to strengthen local administrative capacity, ensure flexible budgetary adjustment mechanisms and better link between the stages of funding programmes.

## Case study no. 3: Thermal rehabilitation of apartment blocks in order to increase energy performance, 9 blocks of flats in Miercurea Ciuc, Harghita county, SMIS code 325468

Source: Site visit

- OBJECT AND PURPOSE OF THE CASE STUDY

The case study provided relevant answers to all evaluation questions, complementing the quantitative data with qualitative information, essential for understanding the context and real impact.

- PRESENTATION OF THE PROJECT OBJECT OF THE STUDY

| Project name | Thermal rehabilitation of apartment blocks in order to increase energy performance, 9 blocks of flats in Miercurea Ciuc, Harghita county |
| --- | --- |
| SMIS Code | 325468 |
| Location | The project proposes the thermal rehabilitation of 9 blocks located at the following addresses in Romania, the Centre Region, Harghita County, Miercurea Ciuc Municipality, respectively: - Str. Revoluţia din Decembrie, nr. 5AB, postal code 530223 - Str. Octavian Goga Nr. 2 AB, postal code 530222 - Str. Octavian Goga, Nr. 4 AB, postal code 530222 - Str. Octavian Goga, Nr. 6 AB, postal code 530222 - Str. Octavian Goga, Nr. 10 AB, postal code 530222 - Str. Narciselor, nr. 6 AB, postcode 530184 - Bradului Street, no. 11 ABCD, postcode 530183 - Str. Cantar, nr. 12-14, postal code 530150 - Str. Inimii, nr. 12-14, postal code 530225 |
| Benefit | MIERCUREA-CIUC MUNICIPALITY |
| Priority / Specific objective | Policy objective: A greener Europe Priority: P3. A region with environmentally friendly communities Specific objective: RSO2.1_Promovarea energy efficiency measures and reduction of greenhouse gas emissions Fund: European Regional Development Fund |
| Project call/ Operation | Investment Priority 3.1 – Supporting energy efficiency, smart energy management and the use of renewable energy in public infrastructure, including public buildings and the housing sector / Operation A – Residential buildings |
| Implementation period (start/end) | 01.07.2024 - 03.01.2025 |
| Project budget | - Value of EU co-financing: 2,883,890.16 lei |
| Project context | The municipality of Miercurea Ciuc is facing harsh winters and an obsolete residential built fund, characterized by high heat losses and high energy consumption. The blocks targeted in the project, built during the communist period, do not meet the current requirements regarding energy performance. At national level, the project contributes to achieving the objectives set by GEO no. 18/2009 and Romania's commitments on reducing greenhouse gas emissions and increasing energy efficiency, in accordance with national and European legislation. At the same time, the intervention is fully in line with the objectives of the European Green Deal and the "Renovation Wave" initiative, supported by European funds, aimed at modernizing the built fund and reducing energy consumption in the residential sector. |
| Project justification | The residential built fund in Miercurea Ciuc, built mainly before 1990, faces a high degree of wear and a low energy performance. The blocks targeted in the project had major heat losses, high maintenance costs and inadequate living conditions, which generated the need for intervention to improve energy efficiency and improve the comfort of the tenants. The need for the project was determined by a combination of technical, economic and social factors, being an essential measure for the modernization of the housing fund, increasing energy efficiency, reducing pollution and improving the quality of life of the inhabitants of Miercurea Ciuc. |
| Description of the investment | The main intervention works proposed to be carried out on each component are: thermal insulation of the external walls with 15 cm stone wool, of the pallets with 2 cm stone wool, of the 10 cm extruded polystyrene base, of the floor above the last level with 20 cm stone wool, of the lower floor with 20 cm expanded polystyrene, changing the carpentry, cladding the interior walls with a 5 cm thermal insulation layer and 5-10 mm plaster, dismantling the installations and equipment apparently mounted on the facades of the buildings and reinstalling them after carrying out the works and repairing the sidewalks. |

- Objectives and Logic of the intervention

Purpose of the project and alignment with the objectives of RSO2.1

General objective of the project: The general objective of the project is to rehabilitate 9 blocks of flats with high energy consumption in order to increase their energy efficiency as well as to reduce their maintenance costs and improve living conditions.

Specific objectives of the project:

1. Reduction of the annual primary energy consumption at the level of 9 apartment blocks in Miercurea Ciuc Municipality, Harghita County, from a total of 5,588,553.38 kWh/year to a total of 3,176,704.21 kWh/year:

- December Revolution apartment building no. 5 AB – from 676,534.92 kwh/year to 313,549.70 kwh/year;

- Octavian Goga Apartment Building No. 2 – from 580,039.74 kwh/year to 344,406.40 kwh/year;

- Octavian Goga Apartment Building No. 4 – from 580,039.74 kwh/year to 344,406.40 kwh/year;

- Octavian Goga Apartment Building No. 6 AB – from 524,743.80 kwh/year to 340,515.63 kwh/year;

- Octavian Goga Apartment Building No. 10 AB – from 526,866.11 kwh/year to 340,515.63 kwh/year;

- Daffodils apartment building no. 6 AB – from 499,634.37 kwh/year to 286,528.04 kwh/year;

- Bradului apartment building no. 11 ABCD – from 777,969.48 kwh/year to 527,285.75 kwh/year;

- Cantar apartment building no. 12-14 – from 804,096.12 kWh/year to 348,103.40 kWh/year;

- Inimii apartment building no. 12-14 – from 618,629.10 kWh/year to 331,393.26 kWh/year;

2. Reducing the amount of CO2 emissions from 9 apartment blocks in Miercurea Ciuc Municipality, Mureș County, from a total of 43.05 kg/m2/year to a total of 23.75 kg/m2/year and generating a positive impact on the environment and climate change:

- December Revolution apartment building no. 5 AB – from 52.32 kg/m2/year to 23.46 kg/m2/year;

- Octavian Goga Apartment Building No. 2 – from 39.28 kg/m2/year to 22.63 kg/m2/year;

- Octavian Goga Apartment Building No. 4 – from 39.28 kg/m2/year to 22.63 kg/m2/year;

- Octavian Goga Apartment Building No. 6 AB – from 35.37 kg/m2/year to 22.36 kg/m2/year;

- Octavian Goga Apartment Building No. 10 AB – from 35.52 kg/m2/year to 22.36 kg/m2/year;

- Daffodils apartment building no. 6 AB – from 48.55 kg/m2/year to 27.14 kg/m2/year;

- Bradului apartment building no. 11 ABCD – from 37.38 kg/m2/year to 24.72 kg/m2/year;

- Cantar apartment building no. 12-14 – from 58.41 kg/m2/year to 24.37 kg/m2/year;

- Inimii apartment building no. 12-14 – from 47.68 kg/m2/year to 24.84 kg/m2/year;

3. Improvement of the housing conditions of 374 households, located within 9 apartment blocks in Miercurea Ciuc Municipality, Chisinau County. Harghita and obtaining a better classification of energy consumption.

Extent to which the intervention was adapted to the specifics of the building concerned

1. Advanced degree of wear and tear of the buildings: The rehabilitated blocks were old buildings, built before 1990, without adequate thermal insulation measures. They had high heat losses through the walls, roof and windows, leading to high energy consumption for heating.

2. High energy consumption: The buildings concerned recorded high annual energy consumption, both for heating and for other needs, which led to:

- high maintenance costs for tenants,

- low thermal comfort in the interior,

- inefficiency in the use of energy resources.

3. High costs for tenants: Thermal energy bills (or gas/electricity, depending on the system) were very high, especially in the cold season. Thermal rehabilitation was a necessity to reduce the financial pressure on families, especially for vulnerable categories.

4. The need to reduce CO₂ emissions: Blocks were a significant contributor to greenhouse gas emissions, mainly due to inefficient heating systems and energy losses. Through the project, the aim was to align with the European and national objectives regarding:

- increasing energy efficiency,

- reducing the carbon footprint.

5. Inadequate living conditions: Before the intervention, many of the homes in the 9 blocks offered thermal comfort conditions below European standards (cold in winter, overheating in summer, humidity, mold). The project aimed to improve the quality of life of the residents.

Alignment with strategic objectives and funding opportunity: The project fits perfectly with the objectives of the Centre Regional Programme and EU policies on energy efficiency in the residential sector. The existence of the financing line allowed access to non-reimbursable funds for a significant impact on local level.

- PROJECT COMPONENTS

| Activities | - Activity: 1. Signing the Financing Contract - 1.1 Signing of the Stage II financing contract - Activity: 2. Project management (post-contractual) - 2.1 Project management - 2.2 Project management consulting - 2.3 Reporting the progress in the implementation of the project, according to the provisions of the financing contract - 2.4 Request for payment/reimbursement of project expenses - Activity: 3. Information and publicity of the project - 3.1 Information and publicity within the project - Activity: 4. Project audit (post-contractual) - 4.1 Project audit - Activity: 5. Project management (pre-contractual) - 5.1. Project management - 5.2 Project Management Consulting - Activity: 6. Project audit (pre-contractual) |
| --- | --- |
| Expected results | # Output indicator Number of households with a better classification of energy consumption (no. of households): 1. At the level of the financing application: - Start of project implementation: 0 households - Final project implementation: 380 households 2. At the level of the block located on Str. Revoluţiei din Decembrie no. 5 AB - Start of project implementation: 0 households - Final project implementation: 28 households + 2 commercial spaces 3. At the level of the block located on Str. Octavian Goga Nr. 2 AB - Start of project implementation: 0 households - Final project implementation: 40 households 4. At the level of the block located on Str. Octavian Goga Nr. 4 AB - Start of project implementation: 0 households - Final project implementation: 40 households 5. At the level of the block located on Str. Octavian Goga Nr. 6 AB - Start of project implementation: 0 households - Final project implementation: 40 households 6. At the level of the block located on Str. Octavian Goga Nr. 10 AB - Start of project implementation: 0 households - Final project implementation: 40 households 7. At the level of the block located on Narciselor Street no. 6 AB - Start of project implementation: 0 households - Final project implementation: 39 households + 1 commercial space 8. At the level of the block located on Bradului Street no. 11 ABCD - Start of project implementation: 0 households - Final project implementation: 78 households + 2 commercial spaces 9. At the level of the block located on Str. Cantar nr. 12-14 - Start of project implementation: 0 households - Final project implementation: 40 households 10. At the level of the block located on Str. Inimii nr. 12-14 - Start of project implementation: 0 households - Final project implementation: 29 households + 1 commercial spaces # Project indicator: Decrease in annual primary energy consumption (kWh/year): 1. At the level of the financing application - start of project 5588553.37 kWh/year - end of project 3098401.75 kWh/year - consumption reduction 249015162kWh/year 2. At the level of the block on Str. Revoluţiei din Decembrie no. 5 AB - project start 676534.92 kWh/year - end of project 313523.75 kWh/year - consumption reduction 363011.17 kWh/year 3.At the level of the block on Str. Octavian Goga Nr. 2 AB - start of project 580039.74 kWh /year - end of project 352175.00 kWh /year - consumption reduction 227864.74 kWh/year 4.At the level of the block located on Str. Octavian Goga Nr. 4 AB - start of project 580039.74 kWh/year - end of project 352175.00 kWh /year - consumption reduction 227864.74 kWh/year 5.At the level of the block located on Str. Octavian Goga Nr. 6 AB - start of project 524743.80 kWh /year - end of project 352175.00 kWh/year - consumption reduction 172568.80 kWh/year 6.At the level of the block located at 10 AB Octavian Goga Street - project start 526866.11 kWh/year - end of project 352175.00 kWh/year 84 - consumption reduction 174691.11 kWh/year 7.At the level of the block located on Narciselor Street no. 6 AB - start of project 499634.37kWh/year - end of project 276561.00 kWh/year - consumption reduction 223073.37 kWh/year 8.At the level of the block located on Bradului Street no. 11 ABCD - project start 777969.48 kWh/year - end of project 438066.00 kWh/year - consumption reduction 339903.48 kWh/year 9.At the level of the block located on Str. Cantar nr. 12-14 - project start 804096.11 kWh/year - start of project 339939.00 kWh/year - consumption reduction 464157.11 kWh/year 10.At the level of the block located on Str. Inimii nr. 12-14 - project start 618629.10 kWh /year - end of project 321612.00 kWh/year - consumption reduction 297017.10 kWh/year |

- PROGRESS IN IMPLEMENTATION

Progress towards objectives (indicators – planned/achieved targets)

| Categories | Indicator | Target | Done | Level of achievement indicator |
| --- | --- | --- | --- | --- |
| Achievement indicators (program) | RCO18_Locuințe with improved energy performance (housing) Less developed region | 380,00 homes | 380,00 homes | Indicator reached100% |
| Result indicators (programme) | RCR29_Emisii of estimated greenhouse gases (tons CO2 equivalent/year) | 520,23 tons CO2 equivalent/year | 506,27 tons CO2 equivalent/year | The CO₂ emissions indicator was met with a better result than expected, with a further reduction of 13.96 tonnes CO₂ equivalent/year (−2.68%) compared to the planned value. |
|  | annual primary energy RCR26_Consum (of which: of homes, public buildings, enterprises, etc.) (MWh/year) | 3,176.70 MWh/year | 3,098.40 MWh/year | The annual energy consumption indicator was met with an additional saving of 78.30 MWh/year, representing a reduction of approximately 2.46% compared to the initial estimate. |

Project achievements and results

| Activity | Results | % |
| --- | --- | --- |
| - Activity: 5. Project management (pre-contractual) - 5.1. Project management - 5.2 Project Management Consulting | # No. of households with a better classification of energy consumption (no. of households): 1. At the level of the financing application: - Start of project implementation: 0 households - Final project implementation: 380 households 2. At the level of the block located on Str. Revoluţiei din Decembrie no. 5 AB - Start of project implementation: 0 households - Final project implementation: 28 households + 2 commercial spaces 3. At the level of the block located on Str. Octavian Goga Nr. 2 AB - Start of project implementation: 0 households - Final project implementation: 40 households 4. At the level of the block located on Str. Octavian Goga Nr. 4 AB - Start of project implementation: 0 households - Final project implementation: 40 households 5. At the level of the block located on Str. Octavian Goga Nr. 6 AB - Start of project implementation: 0 households - Final project implementation: 40 households 6. At the level of the block located on Str. Octavian Goga Nr. 10 AB - Start of project implementation: 0 households - Final project implementation: 40 households 7. At the level of the block located on Narciselor Street no. 6 AB - Start of project implementation: 0 households - Final project implementation: 39 households + 1 commercial space 8. At the level of the block located on Bradului Street no. 11 ABCD - Start of project implementation: 0 households - Final project implementation: 78 households + 2 commercial spaces 9. At the level of the block located on Str. Cantar nr. 12-14 - Start of project implementation: 0 households - Final project implementation: 40 households 10. At the level of the block located on Str. Inimii nr. 12-14 - Start of project implementation: 0 households - Final project implementation: 29 households + 1 commercial space # Decrease in annual primary energy consumption (kWh/year): 1. At the level of the financing application - start of project 5588553.37 kWh/year - end of project 3098401.75 kWh/year - consumption reduction 249015162kWh/year 2. At the level of the block on Str. Revoluţii in Decembrie no. 5 AB - project start 676534.92 kWh/year - end of project 313523.75 kWh/year - consumption reduction 363011.17 kWh/year 3. At the level of the block on Str. Octavian Goga Nr. 2 AB - start of project 580039.74 kWh /year - end of project 352175.00 kWh /year - consumption reduction 227864.74 kWh/year 4. At the level of the block located on Str. Octavian Goga Nr. 4 AB - start of project 580039.74 kWh/year - end of project 352175.00 kWh /year - consumption reduction 227864.74 kWh/year 5. At the level of the block located on Str. Octavian Goga Nr. 6 AB - start of project 524743.80 kWh /year - end of project 352175.00 kWh/year - consumption reduction 172568.80 kWh/year 6. At the level of the block located on Str. Octavian Goga Nr. 10 AB - project start 526866.11 kWh/year - end of project 352175.00 kWh/year 84 - consumption reduction 174691.11 kWh/year 7. At the level of the block located on Narciselor Street no. 6 AB - start of project 499634.37kWh/year - end of project 276561.00 kWh/year - consumption reduction 223073.37 kWh/year 8. At the level of the block located on Bradului Street no. 11 ABCD - project start 777969.48 kWh/year - end of project 438066.00 kWh/year - consumption reduction 339903.48 kWh/year 9. At the level of the block located on Str. Cantar nr. 12-14 - project start 804096.11 kWh/year - start of project 339939.00 kWh/year - consumption reduction 464157.11 kWh/year 10. At the level of the block located on Str. Inimii nr. 12-14 - project start 618629.10 kWh /year - end of project 321612.00 kWh/year - consumption reduction 297017.10 kWh/year | 100% 100% |
| - Activity: 6. Project audit (pre-contractual) |  | 100% |
| - Activity: 1. Signing the Financing Contract - 1.1 Signing of the Stage II financing contract |  | 100% |
| - Activity: 2. Project management (post-contractual) - 2.3 Reporting the progress in the implementation of the project, according to the provisions of the financing contract - 2.1 Project management - 2.4 Request for payment/reimbursement of project expenses - 2.2 Project management consulting |  | 100% 100% 100% 100% |
| - Activity: 4. Project audit (post-contractual) - 4.1 Project audit |  | 100% |
| - Activity: 3. Information and publicity of the project - 3.1 Information and publicity within the project |  | 100% |

The extent to which the project meets the needs of the target groups and socio-economic challenges

- Direct beneficiaries of the project: Approximately 777 people, representing the current tenants of the 375 buildings. Prior to submitting the financing application, the applicant consulted with these tenants on the opportunity to implement the project through this financing program, being obliged to express their agreement to apply for financing through this project and to accept the co-financing share for the apartment, according to the Applicant's Guide.

- The indirect beneficiaries of the project: the Miercurea Ciuc Municipality UAT, due to the increase in the managerial capacity regarding the implementation of the projects as a result of the contribution in the process of elaboration and implementation of the project. Also, another benefit generated at the level of the Miercurea Ciuc Municipality ATU is to increase its attractiveness.

- IMPLEMENTATION PROCESS

Obstacles identified:

- Technical problems specific to the rehabilitation works of old buildings: some structural elements (beams, floors) required replacement, although they were not provided for in the initial project.

- The need to supplement the scaffolding work and adapt the technical details during the execution.

- Cost increases caused by unforeseen works and price updates in the post-pandemic period.

- Difficult coordination between designer and builder, especially in terms of accurately estimating the volume of work.

Implemented solutions:

- The use of the legal provisions regarding the "Miscellaneous and unforeseen" chapter (up to 15% of the value of the general estimate), which allowed the coverage of additional expenses without the need to relaunch the tender.

- Constant collaboration between the management team, designer and builder to adjust technical details and meet deadlines.

- Implementation of financial control measures and technical audit to prevent budget slippage.

- Involvement of the consultant for more effective communication between the parties involved.

Positive elements:

- The beneficiary already had experience in similar projects, including previous rehabilitations financed from its own funds.

- The works were completed and received in full, without administrative blockage or litigation.

- Good collaboration with the Centre RDA and with the project consultant, who ensured a smooth running of the evaluation and contracting stages.

- High degree of satisfaction among the tenants, thanks to the improvement of the thermal comfort and the aesthetic appearance of the blocks.

- ESTIMATED impact

The thermal rehabilitation of 9 collective residential buildings that registered high energy consumption in Miercurea-Ciuc has been completed, works that started on 01.10.2017. As a result of the renovation works, carbon emissions have been reduced, the energy efficiency of the buildings has been increased, and the residents of the 380 homes now benefit from improved thermal and energy conditions, in line with European standards.

The objective of the project was the rehabilitation of 9 residential buildings that registered high energy consumption, in order to increase energy efficiency, reduce maintenance costs and improve living conditions.

In order to achieve this objective, the following thermal rehabilitation works were carried out: insulation and painting of the exterior walls, insulation of roofs and basements, replacement of windows and doors, as well as pouring of protective sidewalks.

As a result of these interventions, the project's indicators were achieved: reduction of greenhouse gas emissions, decrease of annual primary energy consumption, reduction of annual specific energy consumption for heating, as well as increase in the number of households with a better energy classification.

- Energy efficiency: Number of households with a better classification of energy consumption - 380 households;

- Reduction of greenhouse gases: Annual decrease achieved - 520.23 tons of CO2 equivalent/year.

- EFFICIENCY OF the intervention (cost-benefit analysis)

The cost-benefit analysis was integrated into the DALI documentation and carried out by the designer, according to the requirements of the applicant's guide. The results demonstrated the economic and technical viability of the investment, with a favorable ratio between the costs of the work and the energy savings achieved.

Based on the energy audit, the average reduction of primary energy consumption at the level of the 9 blocks is approximately 44%, and the reduction of CO₂ emissions of more than 40% compared to the initial level.

The estimated payback period is approximately 9-11 years, by decreasing maintenance costs and increasing energy efficiency.

The project brought additional benefits:

- improving thermal comfort for over 770 residents,

- reduction of maintenance costs for households,

- increasing the market value of rehabilitated housing,

- reduction of urban pollution and carbon footprint.

By using standardized solutions and a common technical design for all buildings, economies of scale and high efficiency in the use of funds have been achieved.

- Lessons learned and best practices

Factors that favored success:

- Previous experience of the Miercurea Ciuc City Hall in the implementation of thermal rehabilitation projects.

- Integration of all services (design, energy audit, expertise, DALI, PT, technical assistance) into a single contract, which simplified coordination and workflows.

- Good collaboration with the consultant, who ensured efficient communication between the technical and administrative teams.

- Compliance with deadlines and absence of major disputes.

- The quality of the completed works and the visible positive impact on the community.

Barriers and challenges for the future:

- The need for closer collaboration between the designer and the builder at the design stage, in order to better anticipate possible structural problems.

- The importance of introducing clearly defined penalty mechanisms in contracts, in order to comply with the execution deadlines.

- The lack of dedicated campaigns to raise awareness among tenants on the efficient maintenance of buildings after rehabilitation.

- Recommendation to better correlate deadlines and procedures between the different sources of funding (ROP, PR Centre, PNRR), in order to avoid administrative delays.

Replicable best practices:

- Centralization of technical processes in a single integrated contract (design + technical assistance).

- Use of local expertise capital and contractors with experience in thermal rehabilitation.

- Transparency and permanent communication with homeowners' associations.

- CONCLUSIONS

The energy efficiency project carried out by the Municipality of Miercurea Ciuc is an example of good practice in the integrated management of technical, administrative and financial processes within thermal rehabilitation programs. The intervention significantly contributed to improving the quality of life for the inhabitants of the nine included blocks, by increasing thermal comfort and reducing maintenance costs.

Through the phased approach and full integration of design, audit and execution services, the beneficiary was able to ensure an efficient implementation and complete the works without major delays or administrative bottlenecks.

The energy results – reduction of primary energy consumption by around 44% and CO₂ emissions by over 40% – confirm the relevance of the investment and the real impact of European funds on urban sustainability.

The draft also highlights the importance of prudent financial planning and inter-institutional cooperation, including the role of consultant in maintaining communication between technical and administrative teams.

The experience gained provides a solid basis for expanding renovation programs on a larger scale, including through the integration of advanced solutions (heat recovery units, photovoltaic panels, consumption monitoring systems).

In conclusion, the investment made in Miercurea Ciuc demonstrates that energy efficiency is not only a technical requirement, but a strategic investment in the sustainable development of the community, with direct benefits for the population, the environment and the local administration.

Comments on the Evaluation Report

| Comment | Treatment by the evaluation team |
| --- | --- |
| MA RP for the Central Region Reviews |  |
| As for the appearance, please insert on all the pages that it is a draft | Solved. |
| Paragraph 23 on the problems encountered also needs to be supplemented | The paragraph has been completed. |
| Question 4, the chapters Conclusions and Recommendations and the Annexes, which constitute the Reports of interviews, surveys, the methods applied, must also be filled in with information, from which it appears that you have enough data to produce a complete Report | All these elements have been completed. |
| Between the chapters of conclusions and Annexes, please include another chapter with the steps to be taken in the last part of the elaboration of the report – what methods will be applied, who is part of the target groups of the study, etc. – Here, I will ask you to take into account the choice of subjects from all the counties of the Region, to have a balanced and covering point of view | This chapter has been included. We will consider applicants for funding from all counties of the Centre Region. |
| When detailing the provisions of the PNIESC, I propose a comparative approach with the provisions of the PR Center. Please consider using a comparative table, which clearly shows you what the objectives of the PNIESC are and how our Program fits into them. I propose table format, to see in the mirror what is required, what PR Center solves. | The text was organized in tabular form. |
| That's right, but isn't a CdS written well a basic factor for the acquisition to be made difficult? | Revised text. |
| Question A is not seen in its entirety | All graphs have been revised for this purpose. |
| It needs to be filled in, or it is specified when it will be completed. | The response to IE4 has been completed and will be finalized in the 2nd stage of the evaluation. |
| Financing phased projects has advantages and disadvantages. | The text has been revised to maintain a neutral tone. |
| The financing of the auxiliary works was promoted by the MA in discussions with the EC representatives in order to support the beneficiaries, obtaining the agreement to finance them up to 15% of the eligible expenses | The text has been revised to reflect this situation. |
| Issues regarding the use of financial instruments in the intervention should be reflected in the report. | The final evaluation report will also include this aspect, |
| A discussion with the EC representative on the intervention of RSO2.1 would be useful | A discussion will be organized. |
| Paragraph 63 should be reformulated. | The text has been reworded for clarity. |
| The comments received and how they were taken into account by the evaluators will be attached | This document contains the comments received and how they were addressed by the evaluators |
| Here was a phrase with the formula Taro Yamane, too bad you gave it up. | That phrase needs an update, we will do it in the Final Evaluation Report. |
| And ok? Above it says that 2 are members of the CM | Yes, that's right. In total there are 3 CM members, of which 2 are also applicants for funding. |
| Are there solutions to obtain this data (on actual energy consumption) in the future? | Yes, for this purpose, recommendation no. 6 has been formulated for the future programming period. |
| We go directly from Figure 4 to Figure 6 and in Figure 8 we use an English term | The list of Figures has been updated. |
| Comments MA RP for the Central Region (via LOT 2) |  |
| - It should be clearly stated what is being analyzed. How many projects are in implementation and evaluation/contracting (if applicable)? What is their value? It's true that AM knows at this point. But in a few months, when the report is reread, clarity on the exact portfolio of the projects analyzed may also be lost in the MA. In addition, the report is not only addressed to the MA, but it will also be a public document. | Chapter 2 has been introduced. Presentation of the evaluated intervention |
| - from a methodological point of view, even if there is an annex with the detailed methodology, the volume of data on which the analyses are based must be briefly presented in the report | It was included in Chapter 4. Application of the evaluation methodology and analysis of the collected data |
| - There are several situations in the report where it is not clear what data the findings are based on. It should be revised, to ensure the credibility of the evaluation with the mention of the data sources (in the text or, in order not to load the text, in the notes). I have made a number of comments, but there are several places where clarifications are needed on the source of the information | The source of the information is mixed – we triangulated the information – interviews, AM workshop, survey, documentary research. |
| - presenting the conclusions, recommendations and lessons learned after each evaluation question is a solution for organizing the report, leaving only the critical and cross-cutting aspects to be presented at the end of the report. But if you keep this organization, I think a unitary, coherent approach must be ensured. Now we have the IE where the conclusions, recommendations and lessons learned section is developed on several pages, and the IE where it is missing or is reduced to a single paragraph. | In principle, for each evaluation question, all the conclusions and recommendations considered relevant by the evaluators were formulated at this stage, without pursuing as an end in itself the balance in terms of volume of text between the various evaluation questions. If in the next stage of the evaluation the additional information collected indicates the need to complete conclusions, we will do so. |
| - for IE5. "How well do the (initial) objectives of the intervention correspond to the needs identified at local/EU level?", which you mention is addressed to 30%, it seems that the beginning of the response organization does not correspond to the assumptions in the matrix. I suggest you go back to these to guide the formulation of your answer. |  |
| It is necessary, in a paragraph, to present what has been evaluated: the number of projects financed, if there are projects under evaluation/contracting at the time of evaluation, what is the general objective of the projects and what activities are financed. | Chapter 2 has been introduced. Presentation of the evaluated intervention |
| The LoI of the IR should be included in the Annex to the Interim and Final Report | The logic of the intervention was introduced in Chapter 2 of the Report. |
| A very brief presentation of the volume of data collected is required in the text of the report: no. of responses to the survey, no. interviews. | It was included in Chapter 4. Application of the evaluation methodology and analysis of the collected data |
| The table where all the boxes are checked is not very relevant. Information should be reorganized. | The table has been removed, the relevant methodological aspects can be found in Chapter 4. |
| The points below need references. | Reference was made to the Annex with Specialized Literature. |
| It is necessary to mention N, no. of answers for which the analysis is made. The graph is well chosen, but if we have a small number of answers, it is not appropriate to present percentage values. | We will look at what could be presented instead of percentages, suggestions are welcome. |
| It would be useful to highlight in the table which are the solutions considered to reflect technological progress. | The explanation is provided in the paragraph preceding the table |
| Why only for public buildings. The information is also repeated in Table 3. | We can also add to the Final Report a table for residential buildings, with the increase in the number of respondents per residential. At this stage, we considered the narrative explanation of the technological solutions adopted by residential buildings sufficient. Yes, the information repeats itself, being necessary in the context of IE6 as well. I preferred this solution (clarity and ease of reading take precedence over appearance) to avoid sending the reader to a table in another part of the document. |
| It is logical and correct, but it is unclear what the source of these statements is. | We added "According to specialists" – we rely on technical opinions collected in interviews. |
| It is unclear from the wording of the paragraph whether the finding is based on the example extracted from the case study, or on more data (e.g. survey), to which the example is added. | Revised text for clarity. |
| The assumptions in the evaluation matrix should be better followed: The initial premises of the program remain valid for justifying the interventions. - Variations in the premises for substantiating interventions do not affect the typology of actions, objectives (expected results, including targets) and planned achievements - The intervention is supported by a project prioritisatzon mechanism that directly contributes to reducing energy poverty - The current needs are sufficiently addressed. Moreover, at IR we discussed the analysis of the appropriateness of the use of financial instruments at this RSO. This analysis is missing. | All responses to the evaluation questions follow the assumptions in the evaluation matrix, although not in the same format. I used the hypotheses as a checklist, but I didn't organize the text by hypotheses. If necessary, we can explicitly refer to each hypothesis, within the Final Evaluation Report. We will also include aspects of financial instruments in the final report. |
| How many (proportion)? The use of more specific data increases the credibility of the findings. | We will make more precise references in the Final Report. |
| It should be explained how. | We will complete in the Final Report, after the information base is complete |
| A reference to the EA is useful where the way in which these practices influence the projects is described. | I've included the reference. |
| How many (proportion)? The use of more specific data increases the credibility of the findings. | We will complete in the Final Report, after the information base is complete |
| The energy consumption data determines the possibility of calculating the benefits of the project. It would be useful to elaborate on how the beneficiary argues the usefulness and results of the project, without access to data. I don't deny that there is utility, but the way the information is presented helps to understand the problem and the solution adopted. | We have explained in relation to section 4.2. Problems encountered and limitations in the application of the evaluation methodology: the following: Access to quantitative data – energy consumption data and estimated savings are based on consumption standards and technical audit documentation, not actual consumption values. This situation is common in energy efficiency projects, but limits the possibility of measuring (in the future) the real impact of the intervention. |
| It ties in with the idea of paragraph 66 and the paragraphs should be strengthened, or juxtaposed: on the one hand we have a limited perception, but which needs to be analyzed, of bureaucratic and rigid rules and, on the other hand, a perception of an excessive approach in their application, which generates additional challenges and which, although isolated, needs to be addressed: is exclusively related to the conduct of AM | As the finding was not supported by the survey information and was an isolated case, it was removed from the Report. If there is any other information collected at the next stage of the evaluation confirming the finding, we will reconsider. |
| There should be a more coherent approach to how to formulate conclusions after each question. | That section has been supplemented with additional text. In principle, for each evaluation question, all the conclusions and recommendations considered relevant by the evaluators were formulated at this stage, without pursuing as an end in itself the balance in terms of volume of text between the various evaluation questions. If in the next stage of the evaluation the additional information collected indicates the need to complete conclusions, we will do so. |
| The wording is unclear: what does "usual margin of delay" mean? I would give up this evaluation, because otherwise it requires a more in-depth analysis of the data, compared to other programming periods. | Text revised, the evaluation has been deleted. |
| It should be described here, or above where they are presented, what the challenges were. Delays are the consequences of these challenges. | Revised text. The challenges related to procurement processes are already part of everyday life, we have not detailed such an analysis of the challenges that lead to delays because it would not bring added value to the valuation. In short, nothing can change in this regard in the procurement landscape in Romania and in no case as a result of an evaluation report like this one. |
| Repeat the table from ÎE 1. | Yes, the information itself repeats, being necessary in the context of IE6 as well. I preferred this solution (clarity and ease of reading take precedence over appearance) to avoid sending the reader to a table in another part of the document. |
| The portfolio of projects is briefly presented. A presentation of the distribution of projects by counties, areas of residence (large/small/rural) etc. should be added. Also, the intervention logic presented mentions, but does not describe the external influencing factors, which are subsequently tested in the evaluation Moreover, the impact cannot yet be observed and will be assessed at the end of the implementation (in the impact evaluation of the programme), and the unexpected effects are only partially documented, being reserved for the final stage of the evaluation. | In Chapter 2. of the report "Presentation of the evaluated intervention" an analysis of the project portfolio in terms of geographical distribution and residence environment was inserted. The external influencing factors that were tested in the evaluation are listed in the response to EI2. The evaluation does not specifically analyze the impact and unexpected effects of the intervention, and an evaluation question is not formulated for this purpose. |
| Data collection is not completed, and further stakeholder engagement is required. | Data collection continues in the second stage of the evaluation. |
| On the one hand, data collection must continue. On the other hand, there are some limitations on the data presented by the report and to a large extent outside the control of the evaluators. Some quantitative data are based on estimates and not on actual values. For example, the reported energy savings are based on estimated values from energy audits and not on actual consumption. This restricts the possibility of measuring the real impact in the short term. The small number of projects and the current implementation phase affect the volume and credibility of the data. This aspect is beyond the control of the evaluators and is not underscored, but it affects credibility somewhat. | Data collection continues in the second stage of the evaluation. This evaluation does not analyse the actual impact of the intervention, and an evaluation question is not formulated for this purpose. The valuation analyses are based on a portfolio of 30 contracted projects and a portfolio of around 24 projects at various stages of the process (ETF valuation, contracting). The data collected reflects the existing situation and is not affected by the number of projects. |
| For a small number of findings, the source of the data analyzed for the formulation of the findings is not clear | The findings are based on data collected through the mix of methods mentioned in the methodological description. The source of this data are the applicants for funding and MA RP for the Central Region, an aspect that implicitly results from the nature of the data. |
| The intermediary nature means that some quantitative analyses are still limited. For example, the cost-benefit analysis is postponed to the final evaluation report. | The quantitative analyses will be completed in the second stage of the evaluation and reflected in the Final Evaluation Report |
| Some hypotheses remain preliminary and are to be validated after full data collection and analysis. | The validation or invalidation of the hypotheses will be completed in the second stage of the evaluation. |
| As an interim report, they are formulated as 'preliminary findings' and will be consolidated in the final report. | The final findings will be made in the Final Evaluation Report. |
| The report is lengthy and would need some ideas synthesized and an executive summary to be used by stakeholders | The executive summary is the usual solution for readers who prefer synthetic information. This summary will be included in the Final Evaluation Report. |
| Being preliminary, the recommendations are not yet grouped and prioritized in detail. | The recommendations will be finalised in the second stage of the evaluation and included in the Final Evaluation Report. Please note that even in the Interim Evaluation Report, the recommendations are grouped. |
| The formation of the recommendations chapter is better and refers to recommendations for the AM Center for the future period. A similar program. As the proposals for Regulations show, we will have a single National and Regional Partnership Plan, with chapters similar to the current Programs, and most likely with one chapter per region. And I have chapters. So probably AM Center will remain responsible, but not for a program, but for a chapter. But the phrase "Future Center PR Program" induces confusion. | Revised text, both in the Executive Summary and in the Recommendations Chapter. |
| These can also be recommendations for current beneficiaries, for the sustainability of investments. They are not expensive measures and can be implemented by local authorities without major challenges (if there is a will) | The submitted projects have already passed the Energy Audit stage, therefore this official measurement in the current programming period is less feasible. |
| Social impact or needs? | Revised text. |
| I think that 1-2 paragraphs summarizing the findings are very welcome. But in this synthesis of the findings, ideas are introduced that are not found, in this question, among the synthesized findings: namely the idea of demonstration projects. I think the idea should be kept, but introduced to recommendations, but with very small adjustments to the findings: new innovations and technologies are taken over, but with some limitations from the perspective of the NZEB concept (this standard is rarely reached). And thus, the recommendation for demonstration projects can be introduced. | Revised text. |
| Given the synthetic way in which the report is constructed and the way in which the findings in the report are supported by the data in the annexes, I recommend moving this table to the annex and replacing it with a synthetic table in which it is easier to follow the alignment of the PR Centre with each mentioned strategic document. | The table has been kept in its entirety here for the sake of clarity of content. Even if it takes up quite a lot of space by synthesizing the content it would lose its informational value, and the number of readers who consult the annexes is, in our experience, very small. |
| It would be interesting to add an analysis of how to prioritize, beyond description of the criteria. What combination of prioritization criteria can best meet strategic needs and objectives? | The National Long-Term Renovation Strategy indicates certain criteria, of a technical, economic and social nature, but does not define a certain strict combination of criteria for the selection of buildings subject to energy rehabilitation. The ETF evaluation grid of the projects included the most important criteria derived from the strategic documents, which ensured adequate prioritization of the financed buildings. This is already specified in the report. Last but not least, the combination of criteria can vary from one UAT to another, depending on the specifics and local priorities. |
| It can also have a more current dimension: the MA can now recommend beneficiaries monitoring of consumption as a sustainability measure. | The submitted projects have already passed the Energy Audit stage, therefore this official measurement in the current programming period is less feasible. |
| It can also have a more topical dimension: the MA can now recommend the approach to consumer behaviors, for example through open lessons in schools and messages sent to events organized by LPAs, as a sustainability measure. | A recommendation in this regard has been included. |
| MIPE (Ministry of Investments and European Projects) Comments |  |
| The "effectiveness" criterion focuses a lot on the positive and negative factors that influenced the implementation/results of the interventions and less on the answer to the question of whether the interventions achieved the expected results/achieved their objectives? | The evaluation question does not aim at the analysis of the achievement of the expected results/achievement of the objectives, being too early for such an analysis (the projects are still far from being completed). The results observed so far refer to the progress of the implementation (e.g. the fact that procurement processes were carried out, project management, etc.). Therefore, the analysis focuses on the influence of factors on the implementation process and on estimating the influence of factors on expected results. |

Simplified Cost Benefit Analysis for Energy Efficiency in Buildings, European Commission, Euroopean Investment Bank, JASPERS.

The discount rate expresses the idea that a euro earned over ten years is worth less than a euro earned today; therefore, future benefits are converted into present equivalent values for a fair comparison. By applying a discount rate of 3%, all future costs and benefits are "brought into the present", so that they can be correctly compared with each other. This 3% is applied annually, meaning that each year the value of a future benefit is reduced by about 3% to reflect the fact that, over time, money and benefits lose value.